## Tracker
Start up 7/1/26 | Production 8/1/26
Application | Critical? | Application Type | Stakeholders | Meeting Date | Due Date | Met with Srikanth | Mockups Created | Reviewed w/ DEV | Demoed | Deployed | Comments | Tim's Comments
MPS | Pre-Trial | UA Icon | Laureen, Chuck | 2026-02-13 |  | TRUE | FALSE | FALSE | FALSE | FALSE | Add ability to procure 3D specs (gauge x diameter x length/weight). | Is the pricing the same as sheet coil purchasing as we currently see? Need specifications sheet for wire rod purchasing?
Vendor complaints | Low | UA Icon | Laureen, Chuck, Danny J, STR | 2026-03-10 |  | TRUE | FALSE | FALSE | FALSE | FALSE
EDI (electronic data interface) | Low | EDI | Laureen, Chuck, Sal, Joe | 2026-03-11 |  | FALSE | FALSE | FALSE | FALSE | FALSE | Eventually add ability to get EDI from the vendors (current and new).
Coil Receiving | Pre-Trial | UA Icon | Laureen, Chuck | 2026-02-26 |  | TRUE | TRUE | FALSE | FALSE | FALSE | Ability to receive rod, with or without EDI.
Coil Receiving |  | Shopfloor/Web | (Sal, Henry), SP, JG,JS, TO,RS, SR | 2026-03-04 |  | TRUE | TRUE | FALSE | FALSE | FALSE
Scrap & Sales | Low | UA Icon/Web | Laureen, Chuck | 2026-03-05 |  | TRUE | FALSE | FALSE | FALSE | FALSE | Reporting Icon/Ship .Net | Can that be tolled through the supplier as we do with sheet.
Vendor Maintenance | Pre-Trial (screen could be low priority) | Web | Laureen, Chuck, Sales | 2026-03-25 |  | TRUE | FALSE | FALSE | FALSE | FALSE
Quotes | Production | Web | Sales – start with Laura G. and Ron F. | 2026-03-09 |  | TRUE | TRUE | FALSE | FALSE | FALSE | Add a flag to indicate the source - coil vs rod.
Orders | Production | Web | Sales – start with Laura G. and Ron F. | 2026-03-09 |  | TRUE | TRUE | FALSE | FALSE | FALSE | Add a flag to indicate the source - coil vs rod.
IQR | Production | Web | Sales, Technical, STR, RS, Mic, Ron, LG | 2026-03-06 |  | TRUE | TRUE | FALSE | FALSE | FALSE | Add a flag to indicate the source - coil vs rod. | Waiting on technical to provide a spreadsheet 03/24/26 2nd meeting scheduled with SP & TO
Iem Template - SMP Creation | Production | Web | Mic, Ryan, Fabian, Sri, TIm | 2026-04-08 |  | TRUE | FALSE | FALSE | FALSE | FALSE
Item | Production | Web | Sales, Technical, STR, RS, Mic, Ron, LG | 2026-03-06 |  | TRUE | FALSE | FALSE | FALSE | FALSE | Add a flag to indicate the source - coil vs rod, define item with one or more stages and possibly upfront anneal. | Waiting on technical to provide a spreadsheet 03/24/26 2nd meeting scheduled with SP & TO
Machines | Pre-Trial (screen could be low priority) | Web | STR, RS, BillP, MF | 2026-03-25 |  | TRUE | TRUE | FALSE | FALSE | FALSE | Add new machine capabilities.
Alloys | Pre-Trial | Web | Mick, Ryan B., Fabian, STR | 2026-03-06 |  | TRUE | FALSE | FALSE | FALSE | FALSE | Uniquely define a vendor (Vendor + Location + Material Type (Reroll / B2B / Rod)), testing specs and reduction percentages. | 03/24/26 2nd meeting scheduled with SP & TO
Storage area to be identified for rods in form of skids | N/A | Shopfloor | Ryan D./Chuck | In Process |  | FALSE | FALSE | FALSE | FALSE | FALSE | Changes to Tow Motors to store the material? | TBD - working with Naj & Bob on layout & flow
Pass Schedule | Production (screen could be low priority) | Web | TO, RN | In Process |  | FALSE | FALSE | FALSE | FALSE | FALSE | Is a pass schedule even required or is it always in one pass? | Working on a pass schedule system layout.
Planning Application / Algo | Production | Web | Margo/Gavin/Brian R | 2026-04-14 |  | FALSE | FALSE | FALSE | FALSE | FALSE | Ability to plan orders with rod. | 03/26/2026 SP to scheudle followup meeting
Scheduling Application / Algo | Production | Web | Stephen | 2026-03-24 |  | TRUE | TRUE | FALSE | FALSE | FALSE | Ability to schedule orders with rod at the new machine (manual and algo).
Anneal - rod/wire (3D/2D) | ??? | Shopfloor/Web | Dan F. | 2026-03-26 |  | FALSE | FALSE | FALSE | FALSE | FALSE | Rules for loading on to plates, stacking rules, separators, etc. Scheduling algo also might need these.
Flat Wire Machine (New Interface) | Production | Shopfloor | TO, RS, STR, JG, KG | 2026-03-04 |  | TRUE | TRUE | FALSE | FALSE | FALSE | New screen(s) to perform the flat wire transaction. Capture Gauge Trace, Width Trace, welded material for traceability.
Packing | N/A | Shopfloor | TO, RS, STR | 2026-03-05 |  | TRUE | TRUE | FALSE | FALSE | FALSE | Most likely no Inspection Bench changes. Packing only, pack specs, weight capture, etc.
Pack Specs | N/A | Shopfloor/Web | Sales, TO, RS, STR | 2026-03-05 |  | TRUE | TRUE | FALSE | FALSE | FALSE | Packing specs for eye to side or eye to sky to be used at new machine and also at packing line.
Certs | N/A | Web | Mick, Fabian, Ryan B. | 2026-03-27 |  | TRUE |  |  |  |  | Unlikely impact on Certs.
Labels include footage | ?? | Shopfloor | RS, SP, Darlene? | ?? |  | FALSE | FALSE | FALSE | FALSE | FALSE | Possibly new labels? | What are we doping with our tolling labels?
DEEP | ?? | Data Collection | Pat, TO, Ralph | In Process |  | FALSE | FALSE | FALSE | FALSE | FALSE | TBD | TBD - depends on solution used in drawing and mill lubricating processes
Reports (Throughput, Gauge Trace, Width Trace, SPC, Camber) | Pre-Trial | Web | TO, RS, STR, Bill P. | 2026-03-27 |  | FALSE | FALSE | FALSE | FALSE | FALSE
Coil Yield / Cost Ledger | Medium | Web | Jeff G., Ken G. | 2026-03-30 |  | TRUE | FALSE | FALSE | FALSE | FALSE
Wip Rejection | Pre-Trial | UA Icon/Web | STR, RS | 2026-03-27 |  | FALSE | FALSE | FALSE | FALSE | FALSE

## Pass_Schd (hidden)
FL1 | [5 empty] | Furnace |  | FL2
VPS | DB1 | DB2 | 12" Mill |  | Takeup |  | Payoff | Stand 1 |  | Stand 2 |  | Edger | Stand 3 |  | Edger
Input Dia. | Output Dia | Output Dia. | Output Gauge | Output Width |  | Anneal |  | Output Gauge | Output Width | Output Gauge | Output Width | Edge Setup | Outpt Gauge | Output Width | Edge Setup
0.375 | 0.35 | 0.281 | 0.1 | 0.675 | [8 empty] | 0.016 | 0.699
FL1 | [5 empty] | Furnace |  | FL2
VPS | DB1 | DB2 | 12" Mill |  |  |  | Payoff | Stand 1 |  | Stand 2 |  | Edger | Stand 3 |  | Edger
Input Dia. | Die Diameter | Die Diameter | Roll Gap | Output Width |  | Anneal |  | Roll Gap | Output Width | Roll Gap | Output Width | Edge Setup | Roll Gap | Output Width | Edge Setup
0.375 | 0.35 | 0.281 | 0.1 | 0.675 | [8 empty] | 0.016 | 0.699
Add both traversing takeups and payoff.
Are the dnacers and entry guides a constraint or are the optional component dependent upon process. This would determine if they are included in the pass schedule.
Should include tol for gauge and width for each component

## Induction_Wld (hidden)
Feet | Min | fps | DwellT
1000 | 1 | 16.6667 | 10 | 166.6667
1250 | 1 | 20.8333 | 10 | 208.3333
1500 | 1 | 25 | 10 | 250

## Machine Template (hidden)
Max Coil/Bundle OD(In)
Max Coil/Bundle Weight(In)
Max Wire/Rod Dia.(In)
Min Wire/Rod Dia.(In)
Max Coil/Bundle Weight(Out)
Max Coil/Bundle OD(Out)
Max Coil/Bundle Width( Out)
Min Coil/Bundle Width(Out)
Max Surface
Max Coil/Bundle Width( In)
Max Flatness
Row descriptions should be changed to reflect what is displayed here.
Row descriptions should be copied from mill template to reflect what is displayed here.
Tab descriptions should be changed to reflect what is displayed here. Pulled from slitter and mill templates.
Change both descriptions to Flattening Line Schedule
Remove Max # of Cuts column
Remove Max Cuts from description
Remove Number of Cuts column
Remove Max Cuts from description
Column descriptions should be copied from Mill & Slitter Templates to reflect what is displayed here.
New columns should be added for conditional dependenceies. (DB1, DB2, FM1-S1, FM2-S1, FM2-S2, FM2-S3. Data would be to signify A (Active) or I (Inactive).
Change description to "Start From Spool"
Add Flattening to Machine Type.