## Read Me
Flat Wire Mill — Development Plan
Issued August 13, 2026 · 15 stages · 107 work items · 186 days of development effort
What this is
The plan to build the flat wire manufacturing system: what will be built, in what order, how long each part takes, and what that means for the date it is finished. It covers 186 days of development effort across 107 work items, grouped into 15 stages.
It is written to be discussed rather than filed. The sheet we would start on is Delivery Options — it is the decision that everything else follows from.
The sheets
Delivery Options — what each team size delivers, and what would change the date. Start here.
Plan by Stage — the fifteen stages of the build, what each one gives you, and when each lands under each option.
Sprint Schedule — every two-week sprint under each option, with its dates, capacity and workload.
Work Items — the full detail. Every item of work, what it delivers, and the sprint it lands in. Filter it during the discussion.
Milestones and Needs — the dates we are working to, what we need from you, and what sits outside this team.
Assumptions and Risks — what the plan takes as given, and what could move it.
How to read the effort figures
Effort is in days, and a day is one person working for one day. Twenty days of effort is one person for four weeks, or four people for one week — it is a measure of size, not of elapsed time. The elapsed time is on the Delivery Options and Sprint Schedule sheets, and it depends entirely on how many people are working.
Sprints are two weeks, starting Monday 24 August 2026. Working days are counted, not assumed — public holidays are deducted from the sprints that contain them, which is why some sprints are shorter than others.
What these figures do not include
Testing and business analysis. The figures are development only. Quality assurance, business analysis and contingency are planned separately and are additional to every date shown here.
Acceptance testing and machine commissioning. These follow the development completion date; they are not inside it.
Two design decisions still open. An allowance is held for each, and neither is included in any figure on these sheets. Both are on the Assumptions and Risks sheet.
What we need back
A decision on team size — the Delivery Options sheet sets out the three we have costed and what each one delivers.
The four items on the Milestones and Needs sheet marked as needed from you. Two of them gate work that starts early.
Confirmation that the stage order matches your operational priorities. If something matters more than its position suggests, it can be moved.

## Delivery Options
Delivery Options
186 days of development effort. What that means depends on how many people are on it — the three options below are the ones we have costed.
Team size | Sprints | Development complete | Against the end-September target | Against fourth-quarter production
2 developers | 10 | Fri 8 Jan 2027 | +100 days | misses the fourth quarter entirely
3 developers | 7 | Wed 25 Nov 2026 | +56 days | inside the fourth quarter, no trial margin
4 developers | 5 | Fri 30 Oct 2026 | +30 days | inside the fourth quarter, about 8 weeks of margin
What changes the date
Lever | Effect on the date | What it means
Defer the yield, cost and scrap work | Removes about half a sprint at three or four developers. | This is the one phase that is wholly optional for go-live. Yield would be reported the existing way and flat wire scrap routed manually until it lands. It is the first thing we would cut and the last thing that affects an operator.
Complete the platform foundation before the sprints start | Removes two to three sprints from every plan. | The foundation is the largest single block of work and every later stage depends on it. Delivering it in the run-up rather than inside the sprints is the single biggest lever available — but it needs about five developers during that period, which is more than any option on this sheet.
Add a fifth developer | Brings development completion into early October. | Below about four people sustained, no team size reaches the end of September. Each person added shortens the plan roughly proportionally until the sequential dependencies between stages become the limit.
Accept the date the plan gives | No change to scope or team. | All three options land inside or close to the planned production window. Moving the development completion date does not by itself move production, provided acceptance testing and commissioning are scheduled after it rather than alongside it.
Every option above uses the same scope and the same effort. The only variable is how many people are working on it.
These are development completion dates. Acceptance testing and machine commissioning follow them and are not included.

## Plan by Stage
Plan by Stage
The 15 stages of the build, in delivery order. Each row is a block of capability that lands together.
# | Stage | What it delivers | Who uses it | Effort (days) | Work items | Sprint — 2 devs | Sprint — 3 devs | Sprint — 4 devs | Can it be deferred?
1 | Operator screen platform | The shared screen framework, controls and live-data client that every operator screen is built on — built once so no later stage re-invents it. | Platform / foundation | 21 | 9 | S1–S2 | S1 | S1 | No — every screen depends on it
2 | Application services platform | The service that holds the business logic, the live-data feed to the screens, and the machine-write layer — including the simulation mode that lets every screen be built and demonstrated before the machines are wired. | Platform / foundation | 27 | 17 | S2–S3 | S1–S2 | S1–S2 | No — every operation depends on it
3 | Data foundation | The flat wire database, its reference data, and the changes to the existing scheduling system that let it carry flat wire alongside coil. | Platform / foundation | 13 | 7 | S3–S4 | S2–S3 | S2 | No — nothing can be recorded without it
4 | Line status board and live data | The first working end-to-end slice — machine data reaching a live board showing all three lines. Everything built later consumes this same live feed. | Supervisor | 11 | 5 | S4 | S3 | S2 | No — every later stage consumes this live feed
5 | Rod check-in and machine configuration | The core operator entry point — verify the material, complete the inspection, confirm the setup, configure the machine and start the run — plus the station that stages the next rod while the current one is still running. | Line operator (FL1 and FL3) | 15 | 7 | S4–S5 | S3 | S2–S3 | No — the entry point to every run
6 | Active run monitoring | The run screen the operator watches continuously — live gauge and width traces, payoff weights, machine status, and every mid-run action one touch away. | Line operator (FL1 and FL3) | 10 | 6 | S5 | S4 | S3 | No — the operator has no view of the run without it
7 | In-run production events | Everything an operator records without stopping the run — welds, die changes, quality checks, roll corrections and categorised pauses. Grouped because they share the run context and the quality gating between them. | Line operator | 17 | 12 | S5–S6 | S4 | S3 | Partly — individual events could follow go-live, at the cost of paper records
8 | Exception handling | The formal off-ramps — putting suspect material on hold, and removing a rod before it finishes, including the supervisor-approved partial run. | Line operator and supervisor | 12 | 7 | S6–S7 | S4–S5 | S4 | Partly — the material hold could follow go-live; checkout could not
9 | Spool check-in and finishing run | The FL2 operator journey — see what material is waiting, check in a spool, review how it was produced, and run the finishing mill. | Line operator (FL2) | 7 | 7 | S7 | S5 | S4 | No — the finishing line cannot be run without it
10 | Coil completion, labelling and packing | The finish line — confirm the coil, record which rods produced which footage, calculate the weight, print the label and manage the two-coils-per-skid packing rule. | Line operator and packing operator | 12 | 7 | S8 | S5 | S4 | No — there is no finished coil without it
11 | Hybrid continuous operation | The most complex route — one line feeding the other continuously with a single operator confirmation, no intermediate spool, and unbroken traceability from rod to finished coil. | Line operator (FL3) | 4 | 4 | S8 | S5–S6 | S4 | No — the hybrid route would not exist
12 | Reporting and certification | The reporting suite in the tool the quality team already uses, and the traceability that produces a welding-wire certificate of conformance. | Quality and process engineering | 10 | 6 | S8–S9 | S6 | S4–S5 | Partly — reporting could follow go-live; the certificate could not
13 | Administration and reference data | The screens that keep the system running without a developer — alloy properties, tolerance bands, machine configuration and user roles. | Process engineering and administration | 8 | 7 | S9 | S6 | S5 | Partly — reference data could be loaded by hand at first
14 | Yield, cost and scrap | Yield measured the way flat wire is actually produced, cost standards for the new lines, and scrap routed like every other material. | Production control and cost accounting | 11 | 4 | S9–S10 | S6 | S5 | Yes — wholly optional for go-live, and the first thing we would cut
15 | Integration testing, commissioning and go-live | The convergence — full end-to-end runs of all three routes, machine commissioning support, acceptance testing and the move to production. | Quality assurance and commissioning | 9 | 2 | S10 | S7 | S5 | No
Stage effort is rounded to whole days, so the column sums to within a day of the 186-day total rather than exactly to it.
A sprint range means the stage spans those sprints; it does not occupy them exclusively — several stages run alongside each other.

## Sprint Schedule
Sprint Schedule
Two-week sprints from Monday 24 August 2026. Working days are counted, not assumed — public holidays are deducted from the sprints containing them, which is why some sprints are shorter.
2 developers — 10 sprints, development complete Fri 8 Jan 2027
Sprint | Dates | Working days | Team capacity (days) | Planned work (days) | Utilisation | Work items | What is delivered
S1 | 24 Aug – 04 Sep | 10 | 20 | 20 | 101 % | 8 | Operator screen platform
S2 | 07 Sep – 18 Sep | 9 | 18 | 16 | 92 % | 11 | Operator screen platform · Application services platform
S3 | 21 Sep – 02 Oct | 10 | 20 | 20 | 100 % | 13 | Application services platform · Data foundation
S4 | 05 Oct – 16 Oct | 10 | 20 | 21 | 104 % | 8 | Data foundation · Line status board and live data · Rod check-in and machine configuration
S5 | 19 Oct – 30 Oct | 10 | 20 | 20 | 102 % | 12 | Rod check-in and machine configuration · Active run monitoring · In-run production events
S6 | 02 Nov – 13 Nov | 10 | 20 | 19 | 97 % | 13 | In-run production events · Exception handling
S7 | 16 Nov – 25 Nov | 8 | 16 | 16 | 97 % | 12 | Exception handling · Spool check-in and finishing run
S8 | 30 Nov – 11 Dec | 10 | 20 | 21 | 103 % | 13 | Coil completion, labelling and packing · Hybrid continuous operation · Reporting and certification
S9 | 14 Dec – 23 Dec | 8 | 16 | 17 | 104 % | 12 | Reporting and certification · Administration and reference data · Yield, cost and scrap
S10 | 28 Dec – 08 Jan | 9 | 18 | 16 | 88 % | 5 | Yield, cost and scrap · Integration testing, commissioning and go-live
Total | 24 Aug – 08 Jan 2027 | 94 | 188 | 186 | 99 % | 107 | the whole plan
3 developers — 7 sprints, development complete Wed 25 Nov 2026
Sprint | Dates | Working days | Team capacity (days) | Planned work (days) | Utilisation | Work items | What is delivered
S1 | 24 Aug – 04 Sep | 10 | 30 | 31 | 102 % | 14 | Operator screen platform · Application services platform
S2 | 07 Sep – 18 Sep | 9 | 27 | 26 | 96 % | 18 | Application services platform · Data foundation
S3 | 21 Sep – 02 Oct | 10 | 30 | 30 | 99 % | 13 | Data foundation · Line status board and live data · Rod check-in and machine configuration
S4 | 05 Oct – 16 Oct | 10 | 30 | 31 | 102 % | 20 | Active run monitoring · In-run production events · Exception handling
S5 | 19 Oct – 30 Oct | 10 | 30 | 30 | 102 % | 21 | Exception handling · Spool check-in and finishing run · Coil completion, labelling and packing · Hybrid continuous operation
S6 | 02 Nov – 13 Nov | 10 | 30 | 29 | 98 % | 19 | Hybrid continuous operation · Reporting and certification · Administration and reference data · Yield, cost and scrap
S7 | 16 Nov – 25 Nov | 8 | 24 | 9 | 36 % | 2 | Integration testing, commissioning and go-live
Total | 24 Aug – 25 Nov 2026 | 67 | 201 | 186 | 92 % | 107 | the whole plan
4 developers — 5 sprints, development complete Fri 30 Oct 2026
Sprint | Dates | Working days | Team capacity (days) | Planned work (days) | Utilisation | Work items | What is delivered
S1 | 24 Aug – 04 Sep | 10 | 40 | 39 | 98 % | 20 | Operator screen platform · Application services platform
S2 | 07 Sep – 18 Sep | 9 | 36 | 35 | 97 % | 19 | Application services platform · Data foundation · Line status board and live data · Rod check-in and machine configuration
S3 | 21 Sep – 02 Oct | 10 | 40 | 39 | 98 % | 24 | Rod check-in and machine configuration · Active run monitoring · In-run production events
S4 | 05 Oct – 16 Oct | 10 | 40 | 40 | 99 % | 27 | Exception handling · Spool check-in and finishing run · Coil completion, labelling and packing · Hybrid continuous operation · Reporting and certification
S5 | 19 Oct – 30 Oct | 10 | 40 | 32 | 81 % | 17 | Reporting and certification · Administration and reference data · Yield, cost and scrap · Integration testing, commissioning and go-live
Total | 24 Aug – 30 Oct 2026 | 49 | 196 | 186 | 95 % | 107 | the whole plan
Team capacity is the whole team for the whole sprint; planned work is the effort of the items placed in it. Utilisation is one against the other.
Above 100 % means the sprint is planned slightly over capacity and absorbs the difference from the sprint before or after it.
A short final sprint is the tail of the plan, not spare capacity — the work left in it cannot start any earlier.

## Work Items
Work Items
All 107 items of development work, in the order they are built. Use the filters on the header row to narrow to a stage or a sprint.
# | Work item | What it delivers for you | Stage | Who it serves | Area of the system | Effort (days) | Sprint — 2 devs | Sprint — 3 devs | Sprint — 4 devs
1 | Screen framework and fixed shopfloor canvas | Every screen renders identically on the panel and is readable at arm's length, standing, in gloves. | Operator screen platform | Line operator | Operator screens | 1.2 | S1 | S1 | S1
2 | Sign-in, role checks and session handling on every screen | No flat wire screen is reachable without a valid sign-in and the right role. | Operator screen platform | Platform / foundation | Operator screens | 0.9 | S1 | S1 | S1
3 | Screen-to-service connection with a demonstration mode | The whole operator experience can be built and reviewed with realistic sample data before the machines or the database are connected. | Operator screen platform | Platform / foundation | Operator screens | 1.5 | S1 | S1 | S1
4 | The six shared screen controls, built once | The setup table, live trace chart, tolerance display, step wizard, action bar and payoff weight bar are built once and reused, so every screen looks and behaves like one system. | Operator screen platform | Platform / foundation | Operator screens | 9.4 | S1 | S1 | S1
5 | Shared field, readout and alert elements | Input fields, numeric readouts, pass/fail buttons and alert banners behave identically on every screen. | Operator screen platform | Platform / foundation | Operator screens | 2.5 | S1 | S1 | S1
6 | Live data client for the operator screens | Live traces render smoothly and keep up with the machine feed without the panel stuttering or freezing. | Operator screen platform | Line operator | Live data and machine interface | 1.9 | S1 | S1 | S1
7 | Simulated live feed for early review | The line board and run screens can be demonstrated and signed off before any machine is connected. | Operator screen platform | Platform / foundation | Live data and machine interface | 0.9 | S1 | S1 | S1
8 | Network drop handling on the operator screens | A short network drop never leaves the operator looking at a blank screen — the last known state stays visible with a clear message that it is not live. | Operator screen platform | Line operator | Live data and machine interface | 0.6 | S2 | S1 | S1
9 | Operator screen application set up | The screen application is created, configured and connected to the existing plant systems, so every later stage is feature work rather than setup. | Operator screen platform | Platform / foundation | Operator screens | 1.9 | S1 | S1 | S1
10 | Live data service for all three lines | All three lines can be watched live, on any number of screens, without anyone refreshing a page. | Application services platform | Supervisor | Live data and machine interface | 2.8 | S3 | S2 | S1
11 | Service interface published early against sample data | Screen development starts immediately and in parallel, against the real service shape rather than a guess at it. | Application services platform | Platform / foundation | Application services | 4.4 | S2 | S1 | S1
12 | Shared request handling, validation and logging | Every operation is validated and logged the same way, so a rule is written once rather than repeated in each screen. | Application services platform | Platform / foundation | Application services | 1.4 | S2 | S1 | S1
13 | Business services with a demonstration mode | The operator screens integrate with the real service before the database holds any data. | Application services platform | Platform / foundation | Application services | 1.0 | S2 | S1 | S1
14 | Data access layer | Business logic is kept separate from how data is stored, so the storage can be tuned without touching the rules. | Application services platform | Platform / foundation | Application services | 1.8 | S2 | S1 | S1
15 | Data access performance approach | High-volume reads such as the live trace stay fast, while ordinary writes stay simple and safe. | Application services platform | Platform / foundation | Application services | 2.0 | S2 | S2 | S1
16 | Activity logging and audit trail | Every action the system takes is logged, and any machine configuration can be reconstructed after the fact — who set it, to what, and when. | Application services platform | Compliance and quality | Application services | 1.0 | S3 | S2 | S2
17 | Environment configuration | Machine addresses, connection details and timings are set per environment rather than built into the software, so moving from test to production is a configuration change. | Application services platform | IT and deployment | Application services | 1.0 | S2 | S2 | S1
18 | Role-based access rules | Each action admits only the roles that should be able to perform it — operator, supervisor, operations manager, quality, engineering. | Application services platform | Platform / foundation | Application services | 1.4 | S2 | S2 | S1
19 | Consistent error handling | Every failure produces a predictable, translatable message, so the operator sees a clear instruction rather than a technical error. | Application services platform | Line operator | Application services | 0.6 | S2 | S2 | S1
20 | One definition per business value | A status or category means exactly the same thing on the screen, in the service and in the database — they cannot drift apart. | Application services platform | Platform / foundation | Application services | 1.0 | S2 | S2 | S1
21 | System health check | A failing database or machine connection is visible to IT before an operator finds it on the floor. | Application services platform | IT and operations | Application services | 0.6 | S3 | S2 | S2
22 | Live event definitions | Every live update the system broadcasts is defined once, so a screen can never receive something it does not know how to display. | Application services platform | Platform / foundation | Live data and machine interface | 1.4 | S3 | S2 | S2
23 | Live data pacing | The panel stays responsive with all three lines running, by pacing high-frequency measurements while sending important events immediately. | Application services platform | Line operator | Live data and machine interface | 1.4 | S3 | S2 | S2
24 | Machine write service with simulation | Every check-in stage can be built, demonstrated and tested long before the machines are commissioned. | Application services platform | Platform / foundation | Live data and machine interface | 1.4 | S3 | S2 | S2
25 | Application service created | The new service is created to the same pattern as the plant's existing services, so it is maintainable by the team that already supports them. | Application services platform | Platform / foundation | Application services | 1.4 | S2 | S1 | S1
26 | Continuous machine data collection | Machine readings are collected continuously without the system falling behind — under heavy load it reduces detail rather than dropping the feed. | Application services platform | Line operator | Live data and machine interface | 2.8 | S3 | S2 | S2
27 | Existing scheduling system extended for flat wire | Flat wire fits alongside coil in the systems the plant already runs — receiving, planning, scheduling, reporting, yield and costing — without ambiguity, and nothing that reads them today breaks. | Data foundation | Platform / foundation | Data | 4.5 | S3 | S2 | S2
28 | In-process status for flat wire material | Material actively on a flattening line is distinctly tracked and cannot be double-allocated. | Data foundation | Scheduling and planning | Data | 0.4 | S3 | S2 | S2
29 | Alloy properties and tolerance bands | Per-alloy process limits and tolerances are held as data, so they are corrected by an engineer rather than by a software change. | Data foundation | Process engineering | Data | 0.6 | S3 | S2 | S2
30 | Equipment and reference tables | Mill stands, draw dies, edgers, spool types and payoff positions exist as maintainable reference data the rest of the system validates against. | Data foundation | Platform / foundation | Data | 1.2 | S3 | S2 | S2
31 | Rod, run and spool records | Every rod, production run and spool has a permanent record, linked so traceability can be enforced rather than assembled later. | Data foundation | Platform / foundation | Data | 1.0 | S3 | S2 | S2
32 | Production event and output records | Business rules stated in the specification are enforced by the database itself, so they cannot be bypassed. | Data foundation | Platform / foundation | Data | 3.9 | S4 | S3 | S2
33 | One-step database build | Any environment can be built from scratch, and rebuilt safely, with a single script — no manual steps to forget. | Data foundation | IT and deployment | Data | 1.0 | S3 | S2 | S2
34 | Line status board | Floor-wide awareness of all three lines from one screen, without walking the floor. | Line status board and live data | Supervisor | Operator screens | 3.9 | S4 | S3 | S2
35 | Alerts and feed status on the board | The supervisor can tell the difference between "nothing is wrong" and "we are not receiving data" — the two look identical on a naive board. | Line status board and live data | Supervisor | Operator screens | 1.8 | S4 | S3 | S2
36 | Board snapshot on load | The board shows the current state the instant it opens, then stays live, rather than starting blank and filling in. | Line status board and live data | Supervisor | Application services | 1.4 | S4 | S3 | S2
37 | Board query performance | The board stays fast with every supervisor terminal refreshing it at once. | Line status board and live data | IT and operations | Data | 0.4 | S4 | S3 | S2
38 | Threshold alerts | A developing problem — a payoff running low, a measurement drifting — reaches the supervisor before it stops the line. | Line status board and live data | Supervisor | Live data and machine interface | 3.5 | S4 | S3 | S2
39 | Guided rod check-in | A step-by-step check-in that will not let the operator proceed until every gate clears, so the machine is configured correctly and the wrong setup is never silently applied. | Rod check-in and machine configuration | Line operator (FL1 and FL3) | Operator screens | 3.0 | S4 | S3 | S2
40 | Machine configured on operator confirmation | The operator's confirmation configures the machine in one action — the line runs the setup that was confirmed and nothing else. | Rod check-in and machine configuration | Line operator | Live data and machine interface | 1.4 | S5 | S3 | S3
41 | Check-in written safely across systems | A machine or network failure part-way through check-in never leaves a half-configured machine with a run recorded as started. | Rod check-in and machine configuration | Platform / foundation | Application services | 3.0 | S4 | S3 | S3
42 | Payoff bay staging service | Two rods can never be recorded on one bay, even if two operators act at the same moment. | Rod check-in and machine configuration | Platform / foundation | Application services | 2.2 | S5 | S3 | S3
43 | Check-in records with bay rules enforced | One rod per bay and one bay per rod are guaranteed by the data, not by the screen. | Rod check-in and machine configuration | Platform / foundation | Data | 2.4 | S5 | S3 | S3
44 | Bay occupancy live on the board | Bay status on the supervisor board reflects what is physically on the machine right now, not what it was at the last refresh. | Rod check-in and machine configuration | Supervisor | Live data and machine interface | 1.0 | S5 | S3 | S3
45 | Pre-check-in staging station | The next rod is staged and inspected against the idle bay while the current one is still running, so the line runs continuously through the weld. | Rod check-in and machine configuration | Line operator (FL1 and FL3) | Operator screens | 2.0 | S5 | S3 | S3
46 | Active run screen | One screen showing the run live with every action one touch away — the operator never leaves the monitor to record something. | Active run monitoring | Line operator (FL1 and FL3) | Operator screens | 2.6 | S5 | S4 | S3
47 | Live gauge and width trace | Drift is visible as it develops, so the operator can react before it produces out-of-specification material. | Active run monitoring | Line operator | Live data and machine interface + Operator screens | 2.2 | S5 | S4 | S3
48 | Machine and material status strip | Machine state, material in process and which components are active read at a glance from one row. | Active run monitoring | Line operator | Operator screens | 1.6 | S5 | S4 | S3
49 | Order and material detail on the run screen | The operator can check an order tolerance without leaving the run screen. | Active run monitoring | Line operator | Operator screens | 1.6 | S5 | S4 | S3
50 | Run resume and historical profile | The run screen resumes correctly after a reload, and a finished run's measured profile can be reviewed — which is how the finishing line sees its incoming material. | Active run monitoring | Line operator | Application services | 1.0 | S5 | S4 | S3
51 | Trace query performance | Reviewing the trace of a long run stays fast, however much data it holds. | Active run monitoring | IT and operations | Data | 0.6 | S5 | S4 | S3
52 | Weld capture | The induction weld joining the running rod to the staged one is recorded, so output footage is attributed to the correct source rod on a customer certificate. | In-run production events | Line operator (FL1 and FL3) | Operator screens | 1.6 | S5 | S4 | S3
53 | Quality checkpoint capture | A measurement is recorded against tolerance and the operator is routed correctly when it fails, so out-of-specification material is suspended rather than shipped. | In-run production events | Line operator | Operator screens | 1.9 | S6 | S4 | S3
54 | Mid-run roll adjustment | Roll gaps are corrected during the run without editing the approved setup, so the setup stays the record of intent and the correction is recorded against the run. | In-run production events | Line operator (FL2 and FL3) | Operator screens | 2.2 | S6 | S4 | S3
55 | Pause and resume with reason capture | Downtime is categorised and attributable, and every way of resuming — continue, reject material, check out the rod, stay paused — is reachable from one place. | In-run production events | Line operator | Operator screens | 1.9 | S6 | S4 | S3
56 | Mid-run die change | A die change is recorded and, when the reason could affect dimensions, the operator is required to take a quality measurement before the run continues. | In-run production events | Line operator (FL1 and FL3) | Operator screens | 1.9 | S6 | S4 | S3
57 | Single weld record | Both places an operator can record a weld produce one identical record, so the traceability chain has no gaps or duplicates. | In-run production events | Platform / foundation | Application services | 1.0 | S6 | S4 | S3
58 | Die change rules enforced in the service | The required quality check after a gauge-affecting die change cannot be skipped. | In-run production events | Platform / foundation | Application services | 1.0 | S6 | S4 | S3
59 | Quality verdict calculated centrally | Whether a measurement is in specification is decided by the system against the recorded tolerance, never by the screen or the operator. | In-run production events | Quality | Application services | 1.0 | S6 | S4 | S3
60 | Roll correction applied and recorded | A correction reaches the machine and is logged with a measurement, and never alters the approved setup. | In-run production events | Platform / foundation | Application services | 1.0 | S6 | S4 | S3
61 | Pause drives the machine and the clock together | A paused line is genuinely idle at the machine, and its downtime is measured rather than estimated. | In-run production events | Platform / foundation | Application services | 0.6 | S6 | S4 | S3
62 | Every in-run event recorded against run and footage | The live trace, the reports and the customer certificate all read from one record, so they cannot disagree. | In-run production events | Platform / foundation | Data | 1.6 | S6 | S4 | S3
63 | Events appear on the trace immediately | What the operator records and what the screen shows never disagree. | In-run production events | Line operator | Live data and machine interface | 1.6 | S6 | S4 | S3
64 | Suspect material hold | Suspect material is flagged in seconds with its context already filled in, and the supervisor is alerted. | Exception handling | Line operator | Operator screens | 1.6 | S6 | S4 | S4
65 | Rod checkout | A rod removed before it finishes is recorded with the right disposition for how far it got, so material is never left as ghost inventory. | Exception handling | Line operator | Operator screens | 2.0 | S6 | S4 | S4
66 | Part-run rod carry-forward | A rod that has already run is put on the carry-forward path, so its remaining footage is never mistaken for a fresh rod. | Exception handling | Line operator | Operator screens | 1.6 | S7 | S5 | S4
67 | Off-ramps written with their status changes | The disposition recorded and the material status can never disagree. | Exception handling | Platform / foundation | Application services | 2.0 | S7 | S5 | S4
68 | Pending decisions survive a disconnect | Material on hold is never stranded because a terminal disconnected before the decision was made. | Exception handling | Supervisor | Application services | 1.2 | S7 | S5 | S4
69 | Carry-forward recorded on the material | A part-run rod is identifiable at any station, not only inside the run it came from. | Exception handling | Platform / foundation | Data | 2.2 | S7 | S5 | S4
70 | Holds and checkouts reach the supervisor immediately | The supervisor can act on locked material without being told verbally. | Exception handling | Supervisor | Live data and machine interface | 1.2 | S7 | S5 | S4
71 | Spool check-in | The finishing operator checks in a spool and sees how it was produced before running it, so they know what they are finishing. | Spool check-in and finishing run | Line operator (FL2) | Operator screens | 1.2 | S7 | S5 | S4
72 | Spool queue | Every spool available to run is visible without scanning anything, so the operator knows what material is waiting instead of guessing. | Spool check-in and finishing run | Line operator (FL2) | Operator screens | 2.0 | S7 | S5 | S4
73 | Finishing line run screen | The run screen shows spool in and coil out rather than rod payoffs, matching what the finishing line actually does. | Spool check-in and finishing run | Line operator (FL2) | Operator screens | 0.6 | S7 | S5 | S4
74 | Spool check-in and lookup service | Scanning a spool resolves its order and the rest of that order's material in a single step, and checks it in against the finishing line. | Spool check-in and finishing run | Line operator (FL2) | Application services | 1.5 | S7 | S5 | S4
75 | Spool queue performance | The spool queue stays fast as the number of spools grows. | Spool check-in and finishing run | IT and operations | Data | 1.0 | S7 | S5 | S4
76 | Clear labelling where live measurement is unavailable | The finishing line states plainly that it has no live gauge feed, so a drawn line is never read as a real measurement. | Spool check-in and finishing run | Line operator (FL2) | Live data and machine interface | 0.4 | S7 | S5 | S4
77 | Approaching-target notification | The operator is told as a spool approaches its target weight, so the machine stop is expected rather than a surprise. | Spool check-in and finishing run | Line operator (FL1) | Live data and machine interface | 0.4 | S7 | S5 | S4
78 | Coil completion | The finished coil is confirmed with its calculated weight and dimensions, creating the customer-facing record at the moment the coil comes off the machine. | Coil completion, labelling and packing | Line operator (FL2 and FL3) | Operator screens | 1.9 | S8 | S5 | S4
79 | Packing station screen | Finished coils are packed, labelled and skids closed from a station view, without going back to the run screen. | Coil completion, labelling and packing | Packing operator | Operator screens | 1.9 | S8 | S5 | S4
80 | Coil source traceability | Each coil records which source rods produced which footage — the chain a welding-wire certificate is built from. | Coil completion, labelling and packing | Quality | Operator screens | 3.2 | S8 | S5 | S4
81 | Coil label | A correct physical label so the coil is identifiable in the warehouse and on the customer's dock. | Coil completion, labelling and packing | Packing operator | Operator screens | 1.2 | S8 | S5 | S4
82 | Completion creates the record, the genealogy and the skid together | No coil can exist without its traceability — the identifier, the source history and the packing record are created in one operation or not at all. | Coil completion, labelling and packing | Platform / foundation | Application services | 2.1 | S8 | S5 | S4
83 | Overlapping traceability made impossible | A certificate can never attribute the same foot of material to two different rods. | Coil completion, labelling and packing | Quality | Data | 1.2 | S8 | S5 | S4
84 | Completion visible immediately | The board and the packing station reflect completion at once, so the next job starts without anyone asking. | Coil completion, labelling and packing | Supervisor | Live data and machine interface | 0.6 | S8 | S5 | S4
85 | Hybrid check-in and run screens | The hybrid route has its own check-in and run screens, so one confirmation configures both mills. | Hybrid continuous operation | Line operator (FL3) | Operator screens | 1.0 | S8 | S5 | S4
86 | Both mills configured from one confirmation | Material flows continuously through both mills without a second check-in. | Hybrid continuous operation | Line operator (FL3) | Application services | 1.8 | S8 | S5 | S4
87 | Route recorded on every run | Reports and certificates can tell the three production routes apart. | Hybrid continuous operation | Quality and production control | Data | 0.4 | S8 | S6 | S4
88 | Unbroken hybrid trace | The trace runs unbroken from rod to finished coil, so traceability is continuous across the whole hybrid run. | Hybrid continuous operation | Line operator (FL3) | Live data and machine interface | 0.8 | S8 | S6 | S4
89 | Flat wire reporting section | Flat wire reports appear in the reporting tool the quality team already uses — no new application to learn. | Reporting and certification | Quality | Data + Application services | 2.9 | S8 | S6 | S4
90 | Gauge trace report | The measured gauge profile of any run can be reviewed after the fact. | Reporting and certification | Quality | Operator screens + Application services + Live data and machine interface | 1.6 | S8 | S6 | S4
91 | Process capability report | Capability indices across product families, to demonstrate the process is in control. | Reporting and certification | Process engineering | Operator screens + Application services | 1.2 | S9 | S6 | S5
92 | Production detail report | The full pass detail behind a finished coil, so how it was made can be reconstructed. | Reporting and certification | Process engineering | Operator screens + Application services | 1.2 | S9 | S6 | S5
93 | Quality checkpoint report | Every quality checkpoint in one report, so gates can be audited across a shift or an order. | Reporting and certification | Quality | Operator screens + Application services | 1.2 | S9 | S6 | S5
94 | Traceability and certification report | A finished coil traced back to the supplier heat — the report a welding-wire certificate of conformance is issued from. | Reporting and certification | Quality | Operator screens + Application services | 1.2 | S9 | S6 | S5
95 | Three lines registered as plant machines | The three flattening lines are fully configured machines, so scheduling, planning, reporting and the shop floor can all reference them. | Administration and reference data | IT and administration | Operator screens | 0.9 | S9 | S6 | S5
96 | Material type on alloy maintenance | Flat wire and strip are distinguishable wherever alloy data is edited. | Administration and reference data | Process engineering | Operator screens | 0.9 | S9 | S6 | S5
97 | Alloy and tolerance maintenance screen | Alloy properties and tolerance bands are maintained by an engineer without a software change, so reference data is corrected as the mill learns the process. | Administration and reference data | Process engineering | Operator screens | 1.5 | S9 | S6 | S5
98 | Role assignment screen | Operator, supervisor and manager access is managed in the application rather than by a database administrator. | Administration and reference data | IT and administration | Operator screens | 0.9 | S9 | S6 | S5
99 | Administration services with audit | Reference data cannot be changed anonymously — every change records who made it and when. | Administration and reference data | Compliance and quality | Application services | 2.5 | S9 | S6 | S5
100 | Equipment reference maintenance | Mill stands, draw dies, edgers and spool configurations stay maintainable as the plant changes. | Administration and reference data | Process engineering | Data | 0.6 | S9 | S6 | S5
101 | Tolerance changes reach open screens | An operator is never validating against a tolerance band that was changed while their screen was open. | Administration and reference data | Line operator | Live data and machine interface | 0.2 | S9 | S6 | S5
102 | Weight calculated from footage | Weight is derived from footage and cross-section rather than a scale, because flat wire is produced continuously and not weighed during the run. | Yield, cost and scrap | Production control | Operator screens + Application services | 4.1 | S9 | S6 | S5
103 | Yield attributed per source rod | Yield is attributed across weld points to each source rod, so welding-wire certificates carry correct per-rod figures. | Yield, cost and scrap | Quality and production control | Application services | 1.8 | S10 | S6 | S5
104 | Flat wire cost standards | Cost standards exist for the new lines, so costing reports are populated rather than blank. | Yield, cost and scrap | Cost accounting | Application services + Operator screens + Data | 3.1 | S10 | S6 | S5
105 | Scrap outlet selection | Flat wire scrap is routed to the right outlet and handled like every other material. | Yield, cost and scrap | Production control | Operator screens + Application services + Data | 2.1 | S10 | S6 | S5
106 | Machine commissioning support | The system is switched from simulation to live machine control with engineering support on hand, so the mill is configured by the application rather than by hand. | Integration testing, commissioning and go-live | Commissioning and controls engineering | Live data and machine interface | 4.4 | S10 | S7 | S5
107 | Defect resolution allowance | Time is budgeted to fix what the end-to-end runs find, so defects are closed before the trial rather than carried into it. | Integration testing, commissioning and go-live | Quality assurance | Operator screens + Application services + Data | 4.4 | S10 | S7 | S5

## Milestones and Needs
Milestones and Needs
The dates the plan works to, what we need from you to hit them, and what sits outside this team.
Delivery milestones — the end of the sprint that completes them
Milestone | Reached with 2 developers | Reached with 3 developers | Reached with 4 developers | What it means
Platform foundation complete | S4 · 16 Oct 2026 | S3 · 02 Oct 2026 | S2 · 18 Sep 2026 | Screen framework, application services and database in place, with the machine-write layer running in simulation. Everything after this point is feature work.
First live end-to-end slice | S4 · 16 Oct 2026 | S3 · 02 Oct 2026 | S2 · 18 Sep 2026 | Machine data reaching a live line status board. The first point at which the system can be seen working against real equipment data.
Full rod-to-run journey working | S6 · 13 Nov 2026 | S4 · 16 Oct 2026 | S3 · 02 Oct 2026 | Check in a rod, configure the machine, watch the run live, record events against it. The core operator experience end to end.
All three production routes complete | S8 · 11 Dec 2026 | S6 · 13 Nov 2026 | S4 · 16 Oct 2026 | Standalone drawing, standalone finishing and the hybrid route, through to a finished coil with its traceability and label.
Development complete | S10 · 08 Jan 2027 | S7 · 25 Nov 2026 | S5 · 30 Oct 2026 | All planned scope built and internally tested. Acceptance testing and machine commissioning follow this date; they are not included in it.
Stages overlap, so two milestones can land in the same sprint — the plan does not idle between them.
What we need from you, and what sits outside this team
Item | Type | What it means
Tolerance values per alloy | Needed from you | Minimum and maximum values for gauge, width, diameter and ovality, per alloy. Check-in inspection cannot validate anything until these exist, and they cannot be guessed. Needed before rod check-in is built.
Footage-to-weight basis | Needed from you | How a finished coil's weight is derived from its footage — from target dimensions, from measurement at completion, or integrated across the run. It affects the weight printed on every customer label. Needed before coil completion is built.
Customer spool weight range | Needed from you | The minimum and maximum finished weight a customer will accept, so the system knows when a spool is complete and when a short close needs approval.
Machine tag confirmation | Needed from you | Confirmation from the controls engineer of the address of every value the system writes to or reads from the machines. Until confirmed, all machine interaction runs in simulation. Needed before commissioning.
Rod supply and order scheduling | External dependency | Rod receiving and order scheduling are handled by existing systems and separate teams. Check-in has no material and no scheduled job until both are in place — if either slips, this plan slips with it.
Machine availability for commissioning | External dependency | The final switch from simulation to live machine control needs the controllers and the mill available, with engineering support present. It cannot be compressed by adding developers.

## Assumptions and Risks
Assumptions and Risks
What the plan takes as given, and what could move it. Nothing here is hidden in a figure on another sheet.
Item | Type | Detail
Screen designs are final | Assumption | The approved screen designs are treated as the visual specification, so no design time is included. A significant redesign would add effort not shown here.
Existing plant systems are reused | Assumption | Sign-in, machine configuration, planning, scheduling, reporting, rejection, yield and costing are extended rather than rebuilt. No new technology is introduced.
Testing and business analysis are not in these figures | Assumption | The effort shown is development only. Quality assurance, business analysis, acceptance testing and contingency are planned separately and are additional to every date on this sheet.
No onboarding time is included | Assumption | The figures assume developers are productive from day one. A new joiner needs ramp-up time that is not costed here.
The team is smaller than the work requires | Risk — high | None of the three team sizes completes development by the end of September. The dates on the options sheet are the honest consequence. Mitigation: choose deliberately between team size, scope and date rather than discovering the gap late.
Outstanding decisions block specific work | Risk — high | Several items above cannot be built until a decision is made. Mitigation: each is listed with the work it gates, so the sequence can be planned around the answer rather than waiting on it.
Machine commissioning slips | Risk — medium | Commissioning needs the controllers and the mill. Mitigation: every screen and service is built and testable against simulation, so development is not blocked — but go-live is.
Changes to the shared scheduling system affect existing reports | Risk — medium | Extending the existing schema for flat wire touches data that current reports read. Mitigation: a full impact review across the existing systems is planned before the change, with a tested reversal path.
Performance targets are not yet defined | Risk — medium | How often machine data must update, how many screens must be supported at once, and how long history is retained are not yet specified. Mitigation: the live data layer is built to be tuned by configuration, but the targets should be agreed before load testing.
Two areas carry unresolved design questions | Risk — medium | Recovering cleanly when a check-in fails part-way across systems, and the basis for calculating coil weight, are both still open. Mitigation: an allowance is held for each; neither is included in the effort shown.