## Read Me
Flat Wire Mill — Six-Screen Trial Run
Generated from the plan of record on August 29, 2026. Never edit this workbook — edit the plan and rebuild.
Purpose | This workbook is the trial-run plan the client asked for on 14 August 2026: six operator screens working, with user acceptance testing signed off. It is generated from the plan of record, so every figure in it reconciles to that document rather than being maintained separately. The request named 30 September 2026. On the staffed team — three resources at six and a half hours a day, starting 31 August — the work completes 3 November and sign-off follows around 16 November. The Sprint Plan sheet shows what a larger team would buy.
Scope | Six screens — rod check-in, the active run monitor for both lines, the quality checkpoint, the rejection dialog and the finishing-line spool check-in — plus the platform they sit on, pause and resume, and the transaction that creates a finished spool.
Headline | The six screens are 88 hours of screen work. The platform beneath them is 423 hours, which is 54 per cent of the trial. Cutting screens is the weakest lever available; shortening the platform is the strongest, and it is the only place extra people convert directly into calendar time.
Reading order | Start at Effort Summary for the shape of the work, then Sprint Plan for the dates and what a larger team would buy. Work Items is the detail — every task with what it delivers. Blockers is what the plan needs from outside the development team. Deferred Items and Removal Impact are the boundary: what is deliberately not in the trial, and what that costs.
One caution | Effort here is development effort only. Testing, business analysis and contingency are separate and are not included in any figure in this workbook. A day in this workbook is a six-and-a-half-hour day, being the time each resource commits to this project rather than the length of their working day; the hours themselves are unchanged.
Glossary — the only place shorthand appears in this workbook
Short form | Written out
Frontend (Angular) | Frontend (Angular)
Backend (.NET) | Backend (.NET)
Database (SQL Server) (as a discipline) | Database (SQL Server)
Real-time and controller integration | Real-time and controller integration
Quality Assurance | Quality Assurance
Business Analysis | Business Analysis
Sprint 1, Sprint 2, Sprint 3, Sprint 4 | Sprint 1, Sprint 2, Sprint 3, Sprint 4
1A, 1B, 1C | Phase 1A Angular Foundation, Phase 1B Backend Foundation, Phase 1C Database Foundation
Line Status Overview screen … Material Rejection dialog (as a screen) | Dashboard 1 … Dashboard 8
Flattening Line 1, Flattening Line 2, Flattening Line 3 (hybrid) | Flattening Line 1, Flattening Line 2, Flattening Line 3 (hybrid)
Finishing Mill 1, Finishing Mill 2 | Finishing Mill 1, Finishing Mill 2
Traversing Payoff | Traversing Payoff
Statistical Process Control | Statistical Process Control
Work-in-Progress | Work-in-Progress
User Acceptance Testing | User Acceptance Testing
full-time equivalent | Full-time equivalent
Programmable Logic Controller | Programmable Logic Controller
database build script | Database build scripts

## Effort Summary
Effort Summary
Where the 890 hours of development effort sit, by block of work and by discipline. Development only — testing, business analysis and contingency are separate and are not included.
Block of work | Hours | Days (6.5 h) | Share
Phase 1 platform (Angular, Backend and Database Foundations) | 459 | 70.6 | 55 %
Navigation, reconnect and the run index (was Phase 3) | 15 | 2.3 | 2 %
Phase 4 — rod check-in (no rod pre-staging) | 74 | 11.4 | 9 %
Phase 5 — Active Run Monitor Flattening Line 1 shell + the simulator console | 110 | 16.9 | 12 %
Phase 6 — Statistical Process Control + Pause/Resume (no weld, no die change, no roll adjust) | 56 | 8.6 | 7 %
Phase 7 — Work-in-Progress rejection | 31 | 4.8 | 4 %
Flattening Line 1 spool completion — Part B (FW-202) | 67 | 10.3 | 8 %
Phase 8 — Spool Check-in screen + Active Run Monitor Flattening Line 2 | 38 | 5.8 | 5 %
Flattening Lines 2 and 3 run-end write-back (FW-219) | 40 | 6.2 | 5 %
Total | 890 | 136.9 | 100 %
The platform is the largest single block and has not been started. Reducing screen scope is the weakest lever available to this plan; shortening the platform is the strongest.
By discipline
Discipline | Hours | Days (6.5 h) | Share
Frontend (Angular) | 350 | 53.8 | 39 %
Backend (.NET) | 264 | 40.6 | 30 %
Real-time and controller integration | 141 | 21.7 | 16 %
Database (SQL Server) | 135 | 20.8 | 16 %
Total | 890 | 136.9 | 100 %

## Effort by Phase and Discipline
Effort by Phase and Discipline
The staffing grid. A block total does not say whether the work is screen work or service work; this does. Every row is the sum of its own cells and every column sums to its total.
Phase | Frontend (Angular) | Backend (.NET) | Database (SQL Server) | Real-time and controller integration | Total hours | Days (6.5 h) | Sprint
Phase 1A — Angular Foundation | 139 |  |  | 27 | 166 | 25.5 | Sprint 1
Phase 1B — Backend Foundation |  | 156 |  | 75 | 231 | 35.5 | Sprint 1 · Sprint 2
Phase 1C — Database Foundation |  |  | 62 |  | 62 | 9.5 | Sprint 1
Navigation, reconnect, run index | 12 |  | 3 |  | 15 | 2.3 | Sprint 2
4 Rod check-in | 24 | 24 | 15 | 11 | 74 | 11.4 | Sprint 2
5 Active Run Monitor Flattening Line 1 shell + console | 97 | 8 | 5 |  | 110 | 16.9 | Sprint 2
6 Statistical Process Control + Pause/Resume | 30 | 13 | 6 | 7 | 56 | 8.6 | Sprint 2 · Sprint 3
7 Work-in-Progress rejection | 13 | 8 | 5 | 5 | 31 | 4.8 | Sprint 3
FW-202 Flattening Line 1 spool completion | 20 | 29 | 5 | 13 | 67 | 10.3 | Sprint 3
8 Spool Check-in screen + Active Run Monitor Flattening Line 2 | 15 | 12 | 8 | 3 | 38 | 5.8 | Sprint 3
FW-219 run-end write-back |  | 14 | 26 |  | 40 | 6.2 | Sprint 3
Total | 350 | 264 | 135 | 141 | 890 | 136.9
The platform is three unequal problems that genuinely run in parallel, which is why an extra person pays for itself in the first sprint and nowhere else.
Real-time and controller integration is concentrated in the platform: after it, only 39 hours remain across five blocks, so that owner picks up database or service work.
Spool completion is the only block that is service-heavy, and it is also last and gates the finishing line — so that owner holds the end of the schedule.

## Platform Detail
Platform Detail — Phase 1
459 hours, 54 per cent of the trial, not yet started. Broken out to deliverable level because a single figure for the platform is not something anyone can act on.
Sub-phase | Hand-coded basis | Faster basis, full scope | Trial scope | Reduction | Sprint 1 | Sprint 2
Phase 1A — Angular Foundation | 370 | 166 | 166 | — | 166
Phase 1B — Backend Foundation | 519 | 268 | 231 | −37 | 178 | 53
Phase 1C — Database Foundation | 138 | 62 | 62 | — | 62
Total | 1027 | 496 | 459 | −37 h | 406 | 53
Three bases, and they must not be mixed. The hand-coded basis is the estimate of record and includes testing and contingency. The other two are development only.
Only the backend foundation crosses a sprint boundary. The Angular and database foundations must finish in the first sprint or the whole chain after them slips.
All-in, on the trial basis — comparable with the hand-coded column above
Sub-phase | Development | Testing | Contingency | All-in hours
Phase 1A — Angular Foundation | 166 | 33 | 30 | 229
Phase 1B — Backend Foundation | 231 | 46 | 42 | 319
Phase 1C — Database Foundation | 62 | 12 | 11 | 85
Total | 459 | 91 | 83 | 633
Quote the development figure against a team roster and the all-in figure against a budget. Comparing development-only against the hand-coded column overstates the saving: the like-for-like comparison is 584 against 1,027.
Phase 1A — Angular Foundation
Deliverable | Story | Hand-coded | Trial hours
Library scaffold, routing and configuration | FW-N03 | 24 | 15
Shell layout and the 1280×1024 shopfloor canvas | FW-130 | 16 | 10
Route guards, interceptor wiring, error envelope | FW-131 | 12 | 7
Dependency-injection-swappable API client and domain models | FW-132 | 20 | 12
Six shared composite controls @ 20 h | FW-133 | 120 | 75
Four shared primitives + alert-banner @ 8 h | FW-134 | 32 | 20
SignalR client service | FW-135 | 24 | 15
MockSignalRService + the typed event set | FW-136 | 12 | 7
Offline cache sync and the reconnect banner | FW-137 | 8 | 5
Total |  |  | 166
Phase 1B — Backend Foundation
Deliverable | Story | Hand-coded | Trial hours
FlatWire solution + four-project Clean Architecture skeleton | FW-N04 | 16 | 11
Thin controllers over UAController @ 3 h | FW-138 | 45 | 14
MediatR registration and pipeline behaviours | FW-139 | 16 | 11
Dependency-injection registration and the stub/real service swap | FW-140 | 12 | 8
Repository layer | FW-141 | 28 | 14
Dapper and Entity Framework data access + FlatWireDbContext | FW-142 | 24 | 16
Serilog structured logging and the audit log | FW-143 | 12 | 8
Configuration binding | FW-144 | 12 | 8
Token-based authentication and role authorization policies | FW-145 | 16 | 11
Global exception middleware and the response envelope | FW-146 | 8 | 5
FluentValidation and the canonical cross-layer enums | FW-147 | 12 | 8
Health checks | FW-148 | 8 | 5
FlatWireHub — strongly-typed, MessagePack, line groups | FW-080 | 28 | 22
IFlatWireClient typed event contract | FW-149 | 16 | 11
Plant data ingest hosted service + bounded channel | FW-N05 | 32 | 6
Cadence-driven broadcast loop | FW-150 | 16 | 11
PLCTagService skeleton + SimulatePLCTagPush | FW-151 | 16 | 11
ITInhibitService — per-line tag write, conditions 3–5 | FW-205 | 16 | 14
Domain model — 7 aggregates, 13 value objects, invariants | FW-207 | 32 | 21
Domain events — post-commit dispatch to the hub | FW-208 | 8 | 5
⚠ Simulator control surface — steer · stop edge · dropped readings · state read | FW-218 | 18 | 11
Total |  |  | 231
Phase 1C — Database Foundation
Deliverable | Story | Hand-coded | Trial hours
⚠ Shared-schema renames + new columns — CANCELLED, D-32 (was 16 rename + 40 impact audit) | FW-001 |  | 0
INFLAT coil status — CANCELLED, D-32 (was 4 h) | FW-002 |  | 0
FlatWireDB creation, ordered database build script runner, indexes, grants | FW-152 | 12 | 8
Lookup group tables + seed | FW-005 | 16 | 10
AlloyProperty lookup + seed | FW-004 | 8 | 5
Materials group tables | FW-006 | 12 | 8
Runs and Quality/Output group tables | FW-007 | 52 | 31
Total |  |  | 62

## Work Items
Work Items
All 66 pieces of work in the trial, with what each one delivers. Use the filters on the header row to narrow to a sprint or a phase.
Story | Work item | What it delivers | Technical name | Phase or group | Sprint | Hours | Days (6.5 h)
FW-138 | Service endpoints for every screen | Every screen has a service to call. Eight of the fifteen planned are needed for the trial; the other seven belong to work outside it. | Fifteen thin controllers over UAController | Backend (.NET) | Sprint 1 (31 August – 29 September) | 14 | 2.2
FW-139 | Common request handling | Every request is handled the same way, with logging, validation and error handling applied once rather than rebuilt per feature. | MediatR registration and pipeline behaviours | Backend (.NET) | Sprint 1 (31 August – 29 September) | 11 | 1.7
FW-140 | Sample-data and live-data switch | The whole system switches between sample data and live data with one setting. This is what makes the trial demonstrable before the plant is connected. | Dependency-injection registration and the stub/real service swap | Backend (.NET) | Sprint 1 (31 August – 29 September) | 8 | 1.2
FW-141 | Database access layer | One place where the application reads and writes stored data, so a change to the data model touches one layer instead of many. | Repository layer — one per aggregate root | Backend (.NET) | Sprint 1 (31 August – 29 September) | 14 | 2.2
FW-142 | Database connection and mapping | The application can read and write the flat wire database. | Dapper and Entity Framework data access and FlatWireDbContext | Backend (.NET) | Sprint 1 (31 August – 29 September) | 16 | 2.5
FW-143 | Logging and audit trail | Every action that changes the state of material or writes a setting to a machine is recorded with who did it and when. | Serilog structured logging and the audit log | Backend (.NET) | Sprint 1 (31 August – 29 September) | 8 | 1.2
FW-144 | Environment configuration | Connection details, tolerances and update rates are settings rather than code, changeable without a new release. | Configuration binding | Backend (.NET) | Sprint 1 (31 August – 29 September) | 8 | 1.2
FW-145 | Sign-in and permissions | Only an operator can check in material and only a supervisor can approve an override, enforced by the service rather than trusted to the screen. | Token-based authentication and role authorization policies | Backend (.NET) | Sprint 1 (31 August – 29 September) | 11 | 1.7
FW-146 | Consistent failure responses | An unexpected failure returns a readable response the screen can show, never a raw error. | Global exception middleware and the response envelope | Backend (.NET) | Sprint 1 (31 August – 29 September) | 5 | 0.8
FW-147 | Input validation and shared vocabulary | Invalid entry is refused at the boundary with a specific message, and the screens, services and database all use one vocabulary for states and reasons. | FluentValidation, value objects and the canonical cross-layer enums | Backend (.NET) | Sprint 1 (31 August – 29 September) | 8 | 1.2
FW-148 | System health endpoint | One address reports whether the application, the database and the plant connection are each reachable, so a problem is found by monitoring rather than by an operator. | Health checks | Backend (.NET) | Sprint 1 (31 August – 29 September) | 5 | 0.8
FW-207 | Core business rules | The rules that protect the data live in one place and cannot be bypassed by a screen or a service that forgets to check them. Identifiers validate themselves, so a malformed rod or coil number cannot be created at all. | Domain model — aggregates, value objects and invariants | Backend (.NET) | Sprint 1 (31 August – 29 September) | 21 | 3.2
FW-208 | Live updates from business events | When something happens — a run pauses, a weld is recorded, a coil completes — every open screen is told immediately, and only after the change is safely saved. | Domain events and post-commit dispatch | Backend (.NET) | Sprint 1 (31 August – 29 September) | 5 | 0.8
FW-N04 | Application service created | The service behind the screens exists with its layers separated, ready for the first feature. | FlatWire solution and four-project Clean Architecture skeleton | Backend (.NET) | Sprint 1 (31 August – 29 September) | 11 | 1.7
FW-004 | Alloy reference data | Alloy properties are data the business can maintain, not values built into the code. | AlloyProperty lookup and seed | Database (SQL Server) | Sprint 1 (31 August – 29 September) | 5 | 0.8
FW-005 | Equipment reference data | The fixed reference data every screen reads — mill stands, drawing dies, edgers, spool configurations and payoff positions — exists and is populated. | Lookup group tables and seed | Database (SQL Server) | Sprint 1 (31 August – 29 September) | 10 | 1.5
FW-006 | Material records | Rods, spools and production runs have somewhere to be recorded. | Materials group tables | Database (SQL Server) | Sprint 1 (31 August – 29 September) | 8 | 1.2
FW-007 | Run and quality records | Every event an operator records during a run — check-ins, quality checkpoints, pauses, adjustments, rejections and output — has a place to be stored against its run and the footage it happened at. | Runs and Quality/Output group tables | Database (SQL Server) | Sprint 1 (31 August – 29 September) | 31 | 4.8
FW-152 | Database build and rebuild | The database is built from scripts in a known order and can be rebuilt identically at any time, which is what makes a repeatable test environment possible. | FlatWireDB creation, ordered database build script runner, indexes and grants | Database (SQL Server) | Sprint 1 (31 August – 29 September) | 8 | 1.2
FW-130 | Shopfloor screen layout | Every screen is laid out for the panel size it will actually run on, so nothing has to be re-fitted after it is built. | Shell layout and the 1920×1080 shopfloor canvas | Frontend (Angular) | Sprint 1 (31 August – 29 September) | 10 | 1.5
FW-131 | Access control and error handling | A signed-out or unauthorised user cannot reach an operator screen, and a failed request shows one readable message instead of a blank panel. | Route guards, interceptor wiring and the error envelope | Frontend (Angular) | Sprint 1 (31 August – 29 September) | 7 | 1.1
FW-132 | Data access layer for the screens | Screens can be built and demonstrated against sample data before the services behind them exist, which is what allows screen and service work to run in parallel. | Dependency-injection-swappable API client and domain models | Frontend (Angular) | Sprint 1 (31 August – 29 September) | 12 | 1.8
FW-133 | The six shared screen controls | The six controls that appear across the whole application, built once: the pass schedule table and its confirmation bar, the quality trace chart, the guided step wizard, the action bar and the material weight bar. Every one of the six trial screens depends on all six, which is why nothing downstream starts until this is done. | Shared composite controls | Frontend (Angular) | Sprint 1 (31 August – 29 September) | 75 | 11.5
FW-134 | Shared inputs, readouts and warnings | Consistent entry fields, measurement readouts, pass and fail buttons and warning banners across every screen, so the application reads as one system rather than a set of pages. | Shared primitive controls and alert-banner | Frontend (Angular) | Sprint 1 (31 August – 29 September) | 20 | 3.1
FW-N03 | Operator application created | The operator application exists as something the team can build, run and deploy, with its screens routed and its settings in place. | Angular library scaffold, routing and configuration | Frontend (Angular) | Sprint 1 (31 August – 29 September) | 15 | 2.3
FW-080 | Live data broadcast channel | The channel that pushes live readings to every connected screen, separated by line so a screen only receives the line it is showing. | FlatWireHub — strongly-typed, MessagePack, line groups | Real-time and controller integration | Sprint 1 (31 August – 29 September) | 22 | 3.4
FW-135 | Live connection in the screens | The screens hold an open connection and receive readings as they happen, rather than refreshing to look for them. | SignalR client service | Real-time and controller integration | Sprint 1 (31 August – 29 September) | 15 | 2.3
FW-136 | Simulated live feed for the screens | A stand-in live feed so every moving screen can be built and reviewed before anything is connected to the plant. Small, and the single most valuable piece of schedule insurance in the plan. | MockSignalRService and the typed event set | Real-time and controller integration | Sprint 1 (31 August – 29 September) | 7 | 1.1
FW-137 | Offline resilience | A dropped network shows a clear banner over the last known readings instead of an empty screen, and the connection recovers by itself. | Offline cache sync and the reconnect banner | Real-time and controller integration | Sprint 1 (31 August – 29 September) | 5 | 0.8
FW-149 | Live message definitions | One agreed definition of every live message, so the screens and the service cannot drift apart on what a reading contains. | IFlatWireClient typed event contract | Real-time and controller integration | Sprint 1 (31 August – 29 September) | 11 | 1.7
FW-150 | Live reading delivery | Readings are grouped and sent at a steady rate, so a high-frequency measurement feed reaches the screens without overwhelming them. | Cadence-driven broadcast loop | Backend foundation close-out | Sprint 2 (30 September – 20 October) | 11 | 1.7
FW-151 | Machine settings service, with simulation | Machine settings can be written from the application, and simulated instead when no machine is connected. Every check-in stage can therefore be built and demonstrated long before commissioning. | PLCTagService skeleton and SimulatePLCTagPush | Backend foundation close-out | Sprint 2 (30 September – 20 October) | 11 | 1.7
FW-203 | Simulated machine data feed | Realistic live readings without a machine, and steerable — an in-tolerance run, a drifting one, an out-of-tolerance excursion or a line stop can each be reproduced on demand, so the screens are accepted against known conditions rather than whatever the plant happens to be doing. | Plant data feed simulator — a stand-in for the real ingest | Backend foundation close-out | Sprint 2 (30 September – 20 October) | 6 | 0.9
FW-205 | Run-block interlock | The line is prevented from running whenever the system cannot account for what it is producing — no material checked in, or the footage feed missing or invalid. It clears by itself when the cause clears, and it blocks one line without affecting the others. | ITInhibitService — the run-block interlock | Backend foundation close-out | Sprint 2 (30 September – 20 October) | 14 | 2.2
FW-218 | Controls for the simulated machine data feed | A way to drive the simulated line while a run is in progress, so the acceptance run can be performed at all. Three of its ten steps depend on it: pushing a run out of tolerance to prove the automatic quality prompt fires, stopping the line at a chosen instant to prove the spool completion prompt behaves correctly on a brief stop, and interrupting the data feed to prove the machine is blocked when readings go missing. Restarting the feed with different settings cannot do any of this — it ends the run being demonstrated. The controls are for engineers, are never available to an operator, and do not exist at all once the system is connected to a real machine. | Trial control surface for the feed generator — steer, stop, drop, read | Backend foundation close-out | Sprint 2 (30 September – 20 October) | 11 | 1.7
FW-061 | Rod check-in screen | The rod check-in screen — a guided six-step sequence that will not let a run start until the material, the inspection, the measurements and the mill schedule have each been confirmed. | Dashboard 2 — Rod Check-in six-step wizard (Flattening Line 1/Flattening Line 3 (hybrid)) | 4 | Sprint 2 (30 September – 20 October) | 24 | 3.7
FW-082 | Machine configuration on check-in | Acknowledging the schedule is what configures the mill — die sizes, roll gaps, edge type, speed limits and dimensional targets. The machine is never set from a schedule nobody confirmed. | Programmable Logic Controller tag group push on check-in acknowledgement | 4 | Sprint 2 (30 September – 20 October) | 11 | 1.7
FW-157 | Rod check-in transaction | Checking in a rod records the inspection, the measurements and the run before anything is sent to the machine, and marks the rod as being flattened across the business. | POST /checkin/rod and CheckInService | 4 | Sprint 2 (30 September – 20 October) | 24 | 3.7
FW-159 | Check-in write sequence | The check-in writes land in the correct order across two databases, so a failure part-way through cannot leave one rod recorded in two different states. | RodStaging, the check-in write path and the INFLAT write | 4 | Sprint 2 (30 September – 20 October) | 15 | 2.3
FW-062 | Active run monitor | The screen an operator watches for the whole run: live thickness and width against tolerance, machine and material state, and one-touch access to every action that can be taken without stopping. | Dashboard 3 — Active Run Monitor (Flattening Line 1) and Flattening Line 3 (hybrid) variant | 5 | Sprint 2 (30 September – 20 October) | 17 | 2.6
FW-081 | Live quality trace chart | The live quality trace with its target and tolerance band drawn on it, expandable to fill the screen, and able to switch between live readings and a completed run's recorded history. | gauge-trace-chart live streaming, maximize and runtime source toggle | 5 | Sprint 2 (30 September – 20 October) | 18 | 2.8
FW-162 | Run status cards | Machine state, material flow and mill configuration readable at a glance from across the aisle. | run-status-cards | 5 | Sprint 2 (30 September – 20 October) | 13 | 2
FW-163 | Order and material detail panels | Order and material detail available on the run screen without leaving it, and collapsible so it never crowds the quality trace. | info-grid and chart-tab-strip | 5 | Sprint 2 (30 September – 20 October) | 13 | 2
FW-164 | Run lookup and history | A screen can pick a run back up after a refresh or a shift change, and read a finished run's quality history. | GET /run/active, GET /run/{runId}/gaugetrace and RunQueryService | 5 | Sprint 2 (30 September – 20 October) | 8 | 1.2
FW-165 | Fast quality history retrieval | A long run's quality history loads quickly instead of pulling back every individual reading. | sp_GetGaugeTrace | 5 | Sprint 2 (30 September – 20 October) | 5 | 0.8
FW-214 | Engineering console for the simulated machine | One tool an engineer drives all three simulated lines from, so the acceptance run is a few clicks rather than typed commands with a stopwatch — which matters because the run is performed in front of the client and one of its checks is a three-second stop measured against a five-second threshold. It is a separate desktop application, installed only where it is needed, rather than part of the operator system: it is absent from the dashboard inventory and the navigation, it is restricted to engineering and administration accounts, and it stops working entirely once a line is connected to a real machine. Building it separately also means it can be changed and released without touching the operator screens. Several of its controls arrive switched off, because the behaviour behind them is deliberately not being built for the trial. | Simulator control console Database (SQL Server)-sprint one — standalone WinForms desktop tool | 5 | Sprint 2 (30 September – 20 October) | 36 | 5.5
FW-065 | Quality checkpoint capture | Recording a quality checkpoint without leaving the running screen, with the measurement shown against its tolerance, and a direct route to holding the material when it is outside specification. | Statistical Process Control checkpoint dialog | 6 (start) | Sprint 2 (30 September – 20 October) | 15 | 2.3
FW-071 | Pause and resume capture | Downtime is captured with a reason the business can report on, footage is frozen at the moment of the pause, and resuming offers the operator only the outcomes that make sense at that point. | Pause and Resume dialogs | 6 (start) | Sprint 2 (30 September – 20 October) | 15 | 2.3
FW-168 | Quality checkpoint transaction | Checkpoint measurements are stored against the run and the footage they were taken at, and a result outside specification puts the material on hold. | POST /spc and SpcService | 6 (start) | Sprint 2 (30 September – 20 October) | 8 | 1.2
FW-170 | Pause and resume transaction | Pausing and resuming is recorded with its duration, and the machine is idled and restored along with it. | POST /run/{id}/pause and /resume, and RunControlService | 6 (start) | Sprint 2 (30 September – 20 October) | 5 | 0.8
FW-171 | In-run event records | Quality checkpoints, their measurements and pause events have somewhere to be recorded against their run. | The five in-run event tables | 6 (start) | Sprint 2 (30 September – 20 October) | 6 | 0.9
FW-153 | Connection loss handling | A network drop never shows an operator a blank screen. The last known state stays visible with a clear warning until the connection returns. | Alert chips, reconnect banner and cached-state fallback | navigation | Sprint 2 (30 September – 20 October) | 7 | 1.1
FW-155 | Fast active-run lookup | Finding a line's current run stays instant as years of run history accumulate. | FlatWireRun(LineId, Status) index | navigation | Sprint 2 (30 September – 20 October) | 3 | 0.5
FW-204 | Line picker entry screen | An operator arriving at a terminal picks their line and lands on the right screen for whatever that line is doing. It is retired when the full line status board ships. | Minimal landing route — the entry point when Dashboard 1 is out of scope | navigation | Sprint 2 (30 September – 20 October) | 5 | 0.8
FW-172 | Events marked on the quality trace | Actions an operator takes appear on the run's quality trace at the footage where they happened, so anyone reviewing the run afterwards can see what was done and when. | Run-event markers and the LineStatus transitions | 6 close | Sprint 3 (21 October – 3 November) | 7 | 1.1
FW-067 | Material rejection capture | Suspect material is taken out of production with a reason, a decision on what happens to it and a permanent record — raised from wherever the operator noticed the problem. | Work-in-Progress rejection dialog | 7 | Sprint 3 (21 October – 3 November) | 13 | 2
FW-174 | Rejection transaction | A rejection sets the material's status, files it in the held queue and raises an alert to a supervisor. | POST /wipreject, POST /checkout and their services | 7 | Sprint 3 (21 October – 3 November) | 8 | 1.2
FW-176 | Rejection records | Rejections and the decision taken on each have somewhere to be recorded. | WipRejection / RodCheckout tables and the shared coils carry-forward columns | 7 | Sprint 3 (21 October – 3 November) | 5 | 0.8
FW-177 | Supervisor notification | A supervisor is told when material is held, rather than discovering it at the end of the shift. | Exception broadcasts and the supervisor notification | 7 | Sprint 3 (21 October – 3 November) | 5 | 0.8
FW-064 | Spool check-in screen | The finishing line's check-in screen: the arriving spool's quality history and the material it came from, shown before anything is committed, with the mill configuration confirmed separately. | Dashboard 5 — Flattening Line 2 Spool Check-in | 8 | Sprint 3 (21 October – 3 November) | 10 | 1.5
FW-178 | Run monitor for the finishing line | The same run monitor configured for the finishing line, showing one spool draining and one coil filling rather than two rod payoffs. | Dashboard 3 Flattening Line 2 variant configuration | 8 | Sprint 3 (21 October – 3 November) | 5 | 0.8
FW-179 | Spool check-in transaction | Checking in a spool configures the finishing mill and starts its run, and the operator can see what material is waiting to be processed. | POST /checkin/spool and GET /spools | 8 | Sprint 3 (21 October – 3 November) | 12 | 1.8
FW-180 | Spool check-in records | Finishing-line check-ins have somewhere to be recorded, and finding a spool by its order stays fast. | SpoolCheckin table and the SpoolProcessing.OrderNo index | 8 | Sprint 3 (21 October – 3 November) | 8 | 1.2
FW-181 | Honest live reading on the finishing line | The finishing line states plainly that it has no live thickness measurement, instead of drawing a flat line at target that an operator would reasonably read as a real in-tolerance measurement. | Flattening Line 2 null-gauge contract and the Live/Profile binding | 8 | Sprint 3 (21 October – 3 November) | 3 | 0.5
FW-202 | Spool completion and weighing | The transaction that turns a finished run into a real, weighed, traceable spool. The machine stop is confirmed with the weight held at the moment it stopped, the operator can enter a scale weight instead and is warned if the two disagree, and the spool record is created with its source material and footage. Nothing else in the trial creates the spool that the finishing line checks in. | Flattening Line 1 spool completion — stop confirmation, weight basis and the SpoolProcessing write | new | Sprint 3 (21 October – 3 November) | 67 | 10.3
FW-219 | Finished coil recorded plant-wide | A finished coil that the rest of the plant can actually see. Completing a coil currently records it in the flat wire system alone, so packing cannot find it, shipping cannot ship it, certification has no chain back to the rod, and it never reaches cost or yield reporting. This creates the same set of records any other finished coil at United Aluminum has — the coil itself, its link to the order, its genealogy back to the source rod, its cost record, its skid and its shop-floor transaction — either all together or not at all, so the coil is never complete on one system and missing from the others. It also settles where a flat wire skid is recorded: in the existing shop-floor skid register, numbered by the existing rule, with no new table built. | Flattening Lines 2 and 3 run-end write-back into the shared schema | new | Sprint 3 (21 October – 3 November) | 40 | 6.2
| Total |  |  |  |  | 890 | 136.9

## Sprint Plan
Sprint Plan
Four blocks of work from 31 August. The first is the platform; the last is testing and sign-off, which cannot share a sprint with development work at any team size.
Sprint | Dates | Working days | Team | Capacity hours | Planned hours | Utilisation | Content
Sprint 1 (31 August – 29 September) | Mon 31 Aug – Tue 29 Sep | 21 | 3 | 410 | 406 | 99 % | Angular, Backend and Database Foundations, in parallel
Sprint 2 (30 September – 20 October) | Wed 30 Sep – Tue 20 Oct | 15 | 3 | 292 | 301 | ⚠ 103 % | Phase 1 close-out · navigation · 4 · 5 · 6 (start)
Sprint 3 (21 October – 3 November) | Wed 21 Oct – Tue 3 Nov | 10 | 3 | 195 | 183 | 94 % | 6 close · 7 · spool completion · 8 · run-end write-back
Sprint 4 (4–16 November) | Wed 4 Nov – Mon 16 Nov | 9 | 3 + Quality Assurance + Business Analysis | 176 | 0 | — | Regression · de-stub pass · defects · User Acceptance Testing + sign-off
Development completes at the end of the third sprint. The fourth is regression, replacing the assumptions the build stood on, defect fixing, and user acceptance testing with sign-off.
What each staffing option lands
Option | Development complete | Sign-off | Note
3 resources (the baseline — §2.1) | Wed 4 Nov | ~Tue 17 Nov | 890 h ÷ 19.5 h/day = 45.6 working days from 31 Aug, 47 once each block rounds. This is the staffed plan, not an option: it is what the team actually is. (Tue 3 Nov / ~Mon 16 Nov on 869 h, before D-33)
4 resources | ~Mon 19 Oct | ~late Oct | 26.0 h/day → 35 working days. Buys back roughly two and a half weeks. The fourth pair of hands is worth most in Sprint 1, where the three tracks genuinely parallelise
5 resources | ~Thu 8 Oct | ~mid-Oct | 32.5 h/day → 28 working days. Beyond Sprint 1 the chain is sequential, so the fifth resource returns much less than the fourth — see §3
Allowances held outside the hours above
Allowance | Hours | Basis
G2 / OI-39 — cross-database check-in recovery | 24–64 | [CE §2]. Phase 4's estimate is provisional until it closes
OQ-10 / OI-45 — footage→weight dimensional basis | 16–32 | [CE §2] prices it on Phase 9, but TC-167/TC-168 put the same calculation in the spool-completion path this trial builds. See §5.1

## Sprint Allocation
Sprint Allocation
The same work grouped the way it is committed, sprint by sprint, with the subtotal for each group. Every sprint reconciles to the Sprint Plan.
Sprint 1 (31 August – 29 September) — 406 hours
Group | Story | Work item | Hours | Days (6.5 h)
Frontend (Angular) | FW-130 | Shopfloor screen layout | 10 | 1.5
Frontend (Angular) | FW-131 | Access control and error handling | 7 | 1.1
Frontend (Angular) | FW-132 | Data access layer for the screens | 12 | 1.8
Frontend (Angular) | FW-133 | The six shared screen controls | 75 | 11.5
Frontend (Angular) | FW-134 | Shared inputs, readouts and warnings | 20 | 3.1
Frontend (Angular) | FW-N03 | Operator application created | 15 | 2.3
Frontend (Angular) — subtotal |  |  | 139 | 21.4
Backend (.NET) | FW-138 | Service endpoints for every screen | 14 | 2.2
Backend (.NET) | FW-139 | Common request handling | 11 | 1.7
Backend (.NET) | FW-140 | Sample-data and live-data switch | 8 | 1.2
Backend (.NET) | FW-141 | Database access layer | 14 | 2.2
Backend (.NET) | FW-142 | Database connection and mapping | 16 | 2.5
Backend (.NET) | FW-143 | Logging and audit trail | 8 | 1.2
Backend (.NET) | FW-144 | Environment configuration | 8 | 1.2
Backend (.NET) | FW-145 | Sign-in and permissions | 11 | 1.7
Backend (.NET) | FW-146 | Consistent failure responses | 5 | 0.8
Backend (.NET) | FW-147 | Input validation and shared vocabulary | 8 | 1.2
Backend (.NET) | FW-148 | System health endpoint | 5 | 0.8
Backend (.NET) | FW-207 | Core business rules | 21 | 3.2
Backend (.NET) | FW-208 | Live updates from business events | 5 | 0.8
Backend (.NET) | FW-N04 | Application service created | 11 | 1.7
Backend (.NET) — subtotal |  |  | 145 | 22.3
Real-time and controller integration | FW-080 | Live data broadcast channel | 22 | 3.4
Real-time and controller integration | FW-135 | Live connection in the screens | 15 | 2.3
Real-time and controller integration | FW-136 | Simulated live feed for the screens | 7 | 1.1
Real-time and controller integration | FW-137 | Offline resilience | 5 | 0.8
Real-time and controller integration | FW-149 | Live message definitions | 11 | 1.7
Real-time and controller integration — subtotal |  |  | 60 | 9.2
Database (SQL Server) | FW-004 | Alloy reference data | 5 | 0.8
Database (SQL Server) | FW-005 | Equipment reference data | 10 | 1.5
Database (SQL Server) | FW-006 | Material records | 8 | 1.2
Database (SQL Server) | FW-007 | Run and quality records | 31 | 4.8
Database (SQL Server) | FW-152 | Database build and rebuild | 8 | 1.2
Database (SQL Server) — subtotal |  |  | 62 | 9.5
Sprint 1 (31 August – 29 September) — total |  |  | 406 | 62.5
Sprint 2 (30 September – 20 October) — 301 hours
Group | Story | Work item | Hours | Days (6.5 h)
Backend foundation close-out | FW-150 | Live reading delivery | 11 | 1.7
Backend foundation close-out | FW-151 | Machine settings service, with simulation | 11 | 1.7
Backend foundation close-out | FW-203 | Simulated machine data feed | 6 | 0.9
Backend foundation close-out | FW-205 | Run-block interlock | 14 | 2.2
Backend foundation close-out | FW-218 | Controls for the simulated machine data feed | 11 | 1.7
Backend foundation close-out — subtotal |  |  | 53 | 8.2
navigation | FW-153 | Connection loss handling | 7 | 1.1
navigation | FW-155 | Fast active-run lookup | 3 | 0.5
navigation | FW-204 | Line picker entry screen | 5 | 0.8
navigation — subtotal |  |  | 15 | 2.3
4 | FW-061 | Rod check-in screen | 24 | 3.7
4 | FW-082 | Machine configuration on check-in | 11 | 1.7
4 | FW-157 | Rod check-in transaction | 24 | 3.7
4 | FW-159 | Check-in write sequence | 15 | 2.3
4 — subtotal |  |  | 74 | 11.4
5 | FW-062 | Active run monitor | 17 | 2.6
5 | FW-081 | Live quality trace chart | 18 | 2.8
5 | FW-162 | Run status cards | 13 | 2
5 | FW-163 | Order and material detail panels | 13 | 2
5 | FW-164 | Run lookup and history | 8 | 1.2
5 | FW-165 | Fast quality history retrieval | 5 | 0.8
5 | FW-214 | Engineering console for the simulated machine | 36 | 5.5
5 — subtotal |  |  | 110 | 16.9
6 (start) | FW-065 | Quality checkpoint capture | 15 | 2.3
6 (start) | FW-071 | Pause and resume capture | 15 | 2.3
6 (start) | FW-168 | Quality checkpoint transaction | 8 | 1.2
6 (start) | FW-170 | Pause and resume transaction | 5 | 0.8
6 (start) | FW-171 | In-run event records | 6 | 0.9
6 (start) — subtotal |  |  | 49 | 7.5
Sprint 2 (30 September – 20 October) — total |  |  | 301 | 46.3
Sprint 3 (21 October – 3 November) — 183 hours
Group | Story | Work item | Hours | Days (6.5 h)
6 close | FW-172 | Events marked on the quality trace | 7 | 1.1
6 close — subtotal |  |  | 7 | 1.1
7 | FW-067 | Material rejection capture | 13 | 2
7 | FW-174 | Rejection transaction | 8 | 1.2
7 | FW-176 | Rejection records | 5 | 0.8
7 | FW-177 | Supervisor notification | 5 | 0.8
7 — subtotal |  |  | 31 | 4.8
new | FW-202 | Spool completion and weighing | 67 | 10.3
new | FW-219 | Finished coil recorded plant-wide | 40 | 6.2
new — subtotal |  |  | 107 | 16.5
8 | FW-064 | Spool check-in screen | 10 | 1.5
8 | FW-178 | Run monitor for the finishing line | 5 | 0.8
8 | FW-179 | Spool check-in transaction | 12 | 1.8
8 | FW-180 | Spool check-in records | 8 | 1.2
8 | FW-181 | Honest live reading on the finishing line | 3 | 0.5
8 — subtotal |  |  | 38 | 5.8
Sprint 3 (21 October – 3 November) — total |  |  | 183 | 28.2

## Blockers
Blockers
What must close before the work it gates can proceed, and when. Two of the five are values or confirmations owed to us from outside; three are ours to decide.
Number | Blocker | What we need | What it blocks | Needed by | Consequence if late
2 | Tolerance values not supplied | The four minimum and maximum dimensional tolerance values, owed by email. Nothing is currently seeded and both check-in screens check entered measurements against them. | Rod Check-in screen step 3, Spool Check-in screen dimensions | Before Sprint 2 | The measurement check on both check-in screens cannot be finished.
3 | Failure recovery for check-in undecided | An architectural decision on how a check-in recovers when it fails part-way across two databases and the machine. A check-in is not a single all-or-nothing transaction, and the two candidate approaches differ in effort. | Phase 4 is provisional until it closes | Before Sprint 2 | The rod check-in estimate stays provisional and carries a separate allowance of three to eight days.
4 | ✅ Largely answered 15 Aug 2026 — the six roles already exist as sign-in permissions, so none need creating. One detail is still outstanding. | The exact codes used for the six roles. They are recorded in an abbreviated or coded form rather than as the role names we use in the permissions matrix, and we need the two lists lined up — which code corresponds to operator, supervisor, operations manager, engineering/maintenance, quality and administrator. | ~~Every role-gated action in the trial~~ → the Sprint 1 QA0 walkthrough only | ~~Before Sprint 1 closes (28 Aug)~~ → before the Sprint 1 QA0 walkthrough | The supervisor overrides and approvals can be built, but cannot be checked before the trial. A mismatched code does not raise an error — it silently denies a legitimate supervisor, or in the case of the supervisor notification, sends it to nobody.
5 | Spool-completion prompt is not durable | An owner and an allowance for making the machine-stop prompt survive a page refresh and a dropped connection. The database column that holds it was added on 15 August 2026 and the platform sprint's exit criteria now require the behaviour, but no work item covers it — the story that owns spool completion runs two sprints later, and the obligation belongs to the platform. | The spool-completion step of the acceptance run; the platform sprint cannot exit | Inside Sprint 1, with FW-080 | A prompt raised when the line stops is lost the moment an operator refreshes the screen or the connection drops, and a finished spool is left uncommitted. The failure is silent: nothing errors, the screens compile, the durability simply never happens — and with automated tests withdrawn from the server side, nothing detects it.
6 | Three plant-record values await confirmation | Three values that a finished flat wire coil must carry in the existing plant records, each a question about systems that already exist rather than a design choice. First, the transaction name a flat wire coil completion should carry in the shop-floor history, and whether any current report or process filters on that name. Second, whether a finished flat wire coil should carry the existing on-skid status or needs one of its own. Third, what sample number and planned operations it should carry when they cannot be inherited from the rod. We have proposed an answer to each and each is a single-line change if the answer differs. | FW-219 running anywhere but DEV; the §8 acceptance run if it is executed against a shared database | Before the trial deploys outside DEV — ask now, it is a short conversation | The work can be built and tested against development copies, but must not run against live plant data. Getting one of these wrong does not raise an error — it writes a value an existing report may quietly filter out, and the impact review that would have identified which reports care was removed along with the shared-schema migration.
Second tier — none of these stops the build
Blocker | What we need | Consequence if late
Nine open questions with agreed workarounds | Answers in due course on the footage-to-weight basis, which identifier the spool check-in scans, how a spool produced on the hybrid line is treated at the finishing line, what happens when no schedule matches, which order field carries the coil weight range, how a short close is transacted, and the live-data performance targets. | None immediately. Each has an agreed assumption the trial builds against, and a pass is scheduled in the final sprint to replace those assumptions once answers arrive.

## Deferred Items
Deferred Items
330 hours deliberately outside the trial and why each is safe to defer. All of it remains in the wider delivery — none of it is cancelled.
Deferred | Hours | Days (6.5 h) | Why it is safe to defer for a trial
Line Status Overview screen FW-060 + FW-154 | 42 | 6.5 | Client direction, 14 Aug 2026. See §1.5 for what goes with it
Rod Pre-Check-in station + weld FW-N01, FW-158, FW-160, FW-063, FW-166 + 2 tables | 70 | 10.8 | Client direction, 14 Aug 2026. See §1.5
FW-001 shared-schema renames — CANCELLED outright, D-32, 18 Aug 2026; no longer a descope decision | 36 | 5.5 | Highest blast radius in the plan — the Coil/Bundle… renames land on the shared coils/scheduling schema that the legacy ual-dot-net tier and existing reports read. A trial does not need it; production does. Keep FW-002 (INFLAT)
FW-N05 real Plant data ingest | 22 | 3.4 | Factor 1.00 work — [DE §1] prices it as "not verifiable without the hardware". Belongs in the October commissioning window; the trial runs on a simulated feed + SimulatePLCTagPush
FW-N06 alert rules engine | 28 | 4.3 | Its only consumer was Line Status Overview screen's alert bar
Spool completion Part A (FR-130–FR-136) | 25 | 3.8 | Explicitly Should and "advisory and non-blocking". Part B is Must and stays — see §5.1
FW-073 die change · FW-167 | 23 | 3.5 | Grey the Active Run Monitor button; state "not in trial scope"
FW-070 roll adjust · FW-169 | 26 | 4 | Flattening Lines 2 and 3 only (FR-107–FR-109); grey on the Active Run Monitor for Flattening Line 2
FW-072 rod checkout · FW-173 · FW-175 | 39 | 6 | Resume ships with three of its four outcomes; Check out rod disabled
FW-124 Spool Queue screen spool queue · FW-N02 | 19 | 2.9 | Spool Check-in screen's Browse spool queue → greyed. The scan still validates — GET /spools ships in FW-179
Total | 330 | 50.8

## Removal Impact
Removal Impact
Two screens were removed from the trial on 14 August. Neither was a clean subtraction. These are the consequences, stated so they are decisions rather than discoveries at sign-off.
Removed | Consequence | How it is handled
Dashboard 1 — Line Status Overview | Every one of the six mockups' back button targets dashboard_1_line_status.html, and Spool Check-in screen's Cancel does too. The trial has no entry point and no way back into a running line | A minimal landing route, 5 h — a two-tile line picker routing to Rod Check-in screen/Spool Check-in screen when a line is idle and Active Run Monitor when it is running. It reuses GET /run/active?line= (FW-164, already in scope), so it needs no new endpoint
Dashboard 1 — Line Status Overview | FR-079a — Acknowledge returns the operator to Rod Pre-Check-in station, which is also now out of scope | Acknowledge → Active Run Monitor active run. That was the behaviour until 1 Aug 2026 and it is the natural trial flow. TC-079a does not apply; OI-109 was awaiting client confirmation anyway, so nothing settled is being overridden
Dashboard 1 — Line Status Overview | The Statistical Process Control dialog's read-only mode loses its only caller — Line Status Overview screen's "Statistical Process Control · Last check 07:38 AM · In spec · View →" | Keep the readOnly input on fw-spc-checkpoint-dialog so re-adding Line Status Overview screen is not rework, but no trial path exercises it
Dashboard 1 — Line Status Overview | ⚠ AlertRaised/AlertCleared have no consumer. Line Status Overview screen's alert bar was the only one | The Work-in-Progress rejection's supervisor alert has no visible destination in the trial — the event fires and nothing displays it, so "a rejection notifies someone" cannot be demonstrated. Same class as gap G31. Raise with the client
Dashboard 1 — Line Status Overview | 20 test cases drop out — TC-490…TC-509 | Out of trial scope; they return with Line Status Overview screen
Dashboard 2A — Rod Pre-Check-in, and weld capture | ⚠ No weld markers on either gauge chart. Phase 5's Active Run Monitor live trace and Spool Check-in screen's Flattening Line 1 historical profile both specify vertical weld markers with rod alpha (FR-093, FR-120); with no WeldEvent rows there are none | Build both charts' marker layer — it is part of FW-081/FW-064 and the data contract carries weldMarkers[] — but it renders empty in the trial. Do not delete it; an empty marker array is a legitimate state
Dashboard 2A — Rod Pre-Check-in, and weld capture | ⚠ The trial demonstrates a single-rod spool only. No rod-to-rod join means no multi-rod genealogy, no continuous feed through a weld, and the welding-wire customer-certificate chain is not exercised | CoilTraceability genealogy is an MVP-1 obligation (phase-09, NFR012) and this is the one removal that touches it. Raise with the client explicitly — the trial will not show the traceability the certificates depend on
Dashboard 2A — Rod Pre-Check-in, and weld capture | 55 test cases drop out, and 25 of them are labelled contractual — TC-040…TC-069 (pre-check-in) and TC-190…TC-214, which [TCS §5.6] heads "the contractual suite" | A defensible scope call, but it should be a visible one at sign-off. The suites are unchanged and return with the feature
Dashboard 2A — Rod Pre-Check-in, and weld capture | Rod Check-in screen's payoff selector is now always editable — CHK005's pre-filled/read-only branch has no trigger | Build the direct-check-in fallback only. This is the simpler of the two paths phase-04 describes
Dashboard 2A — Rod Pre-Check-in, and weld capture | FW-202's source-rod list degrades to one rod — its acceptance criterion reads "source rods from the run's WeldEvent chain" | Correct as written; with no welds the chain is one rod long. The story is not trimmed — it is MVP-1 scope and its criteria stay complete
Dashboard 2A — Rod Pre-Check-in, and weld capture | PayoffStateChanged has no publisher and no consumer | Both ends were Rod Pre-Check-in station and Line Status Overview screen. Nothing else referenced it
The two consequences to carry into a sign-off conversation: the trial exercises no weld traceability, so the genealogy behind the welding-wire certificates is not demonstrated; and no screen in the trial displays an alert, so a rejection notifying a supervisor is verifiable only in the message log.