📌 Meeting Summary – Shopfloor Review & Flatwire Requirements

Date: April 16, 2026
Duration: ~1 hr 29 mins
Primary Objective:
Review Flatwire machine requirements, clarify open items, align on shopfloor + web application changes, and define next steps & priorities for implementation.

👥 Attendees

- Srikanth Prabhala – Overall coordination & prioritization

- Tim O’Brien – Flatwire machine owner / process lead

- Jaspreet Singh – Shopfloor requirements & system integration

- Waseem Khan – Web & data-recording applications

- Ritika Raheja – Web UI / item & order changes

- Vicky Arora – Receiving, EDI, inventory impacts

- Sushant – Throughput / data recording (limited availability)

- Bob Scott

- Additional team members joined intermittently

🧠 Key Discussion Summary

1. Flatwire Machine – Purpose & Overview

- UA is entering a new market by producing flat wire (oscillate wound) instead of traditional strip coils.

- Benefits:

  - Lower cost vs pancake coils

  - New customer opportunities

- Machine supports:

  - FL1 (12” mill)

  - FL2 (3-stand finishing mill)

  - Hybrid mode (FL3) – continuous run without intermediate anneal (future).

Key clarification:
This is treated as one logical pass, with multiple components enabled/disabled via pass schedule, not multiple traditional mill passes.

2. Process Flow (High Level)

- Wire rod receiving (AROD)

- Wire drawing (DB1 & DB2) – roundness correction

- 12” flattening mill

- (Optional) Anneal

- 3-stand finishing mill

- Final take-up / packaging

Components can be bypassed depending on the pass schedule (critical concept for PLC & system logic).

3. Pass Schedule – Central Control Concept

- Pass schedule determines:

  - Which components are ON / OFF

  - Die sets, edge sets, roll clearances

  - Gauge & width targets

- NOT auto-generated

- Maintained by Operations / Maintenance

- At material check-in, system must:

  - Read pass schedule

  - Update PLC tags

  - Drive machine behavior dynamically

This is the most critical dependency for the entire solution.

4. Shopfloor & Web System Changes

Receiving (Rod Material)

- Rods received without EDI initially

- Differences from coil receiving:

  - No width

  - Gross/net weight only

  - Different validation rules

- Likely requires:

  - New tab / checkbox for Rod Receiving

  - Separate logic from coil flow

Order / IQR / Item Template

- New indicators:

  - Flatwire flag

  - Edge type (flat / round)

  - Bundle width (oscillation width, not strip width)

- Item template enhanced:

  - Step-level input/output type & shape

  - Supports future flexibility (rod → flat wire → flat wire, etc.)

- Width control moved out of item template → handled via pass schedule.

5. SPC, Quality & Data Recording

- Automatic gauge control (AGC) on mills

- Gauge + width trace recorded (like existing mills)

- Output weight calculated via length, not scale

- Data recording must handle:

  - 12” mill transactions

  - 3-stand mill transactions

- One common UI, multiple running instances allowed

6. Welding & Traceability

- Induction welding for rod-to-rod

- Laser welding for flat-to-flat (optional)

- Welding:

  - Saves setup time

  - Improves yield

- System must support traceability, even if welding itself is manual.

7. Timeline & Deployment Expectations

- Machine setup & PLC commissioning: target end of June

- Trials: July 1

- Production start: August 1

- Software window:

  - ~10 weeks effective development time

- Focus on critical-path functionality first, defer non-blocking features.

✅ Key Decisions

- No Angular/frontend receiving changes for now

- No EDI in Phase 1 (manual receive only)

- One shared interface for:

  - FL1 & FL2 check-in

  - FL1 & FL2 transactions

- PLCs are new, OPC servers remain the same

- Width validation handled via machine/pass schedule, not item template

📝 Action Items

🔧 Process / Engineering

- Finalize Pass Schedule definition

- Provide machine capability specs (min/max gauge & width)

- Confirm which components are mandatory for Day-1 production

💻 Web / IT

- Review full requirements by module

- Identify:

  - Critical vs deferrable features

  - Affected applications (check-in, data recording, receiving)

- Design single UI supporting dual-machine operations

- Plan PLC tag mapping with pass schedule inputs

📦 Receiving / Inventory

- Formalize Rod Receiving screen changes

- Confirm validation rules & storage flows

- Document differences vs coil receiving

📅 Project Planning (Next Steps)

- Next week: Requirement clarification & ownership

- Following week: Estimation + resource mapping

- Early May: Development start

- Continuous review of critical go-live scope